INFORMATION

On the “Western Europe-Western China” International transit corridor

Reconstruction Project

km 774-806 (LOT 2) in South-Kazakhstan region

on the 06.04.2016

General Contractor –  «EVRASCON» JSC Evro-Asian Construction Corporation (Azerbaijan)

Contract EBRD/CW-02/2013 (22/08/2014)

Contract price – 12 585 798 659,48 tenge

Amount of advance  – 1 887 869 798,91 tenge (28/12/2014)

Construction Supervision Consultant –«KazDorNII» in association with «KazNiiPI»  Dortrans and KHA

Time for Completion – 18 months (540 days)

Project Designer – SK «Engineering» LLP

- Main aspects of the project

| Section length (km) | 32 |
| --- | --- |
| Culverts, including: (nos) - cattle underpass | 99 3 |
| Traffic interchange in two levels (nos) | 2 |
| Bridges, overpasses, driveways for agricultural machinery (nos) | 3/2/5 |
| Earthworks (thous. m3) | 697,58 |
| Gravel and sand mix С-4 for subbase with thickness Н=35cm(thous. m3) | 566,90 |
| Crushed stone base course С-6 treated with cement 7%, thickness Н=20cm(thous. m3) | 176,86 |
| Concrete pavement type Btb-4,8 – bending tensile strength; B-35 compression strength; thickness Н=27cm(thous. m3) | 157,64 |
| Bus shelters / Stopping points / Pedestrian underpass 4mх45,73m (nos) | 10/10/2 |
| Rest area with repair trestle (nos) | 1 |

- Laboratory:

Mounting works on the Contractor’s laboratory are completed. The laboratory is located at the production base km 780 (right side). Arrangement of the laboratory is completed. Certification and tools examination have been performed.

- Production base (12 he. at km 780, right side)

All the buildings as follows: office, canteen, laboratory, dormitories for engineering staff and labors. At the present time 5 dormitories for 300 places and the canteen are being operated.  Conducted works on editing of 6 dormitories into 60 places. Office for the Engineer’s Service is provided at the production base.

Concrete batching plant «Jaguar» (production capacity 125 m3/hour) has been installed and produces concrete for production base needs (dormitories and etc.). Concrete batching plant is equipped with 3 cement silos of total capacity 450 tons. The second concrete batching plant with production capacity 180 m3/hour is being installed (100%) with 1 silos for cement of total capacity 500 ton. On base preparation of the foundation under asphalt concrete plant is conducted. A mobile crushing plant produced by TEREXS with production capacity 180 ton/hour has been arranged at the production base, composed as follows: sieve – 2 pc., cone – 1 pc. Executed installation and put into on operation mechanical facility with production capacity 180 ton/hour for producing crushed stone and sand mix added by cement, and equipped by cement silo of 150 ton capacity. A Plant for production reinforce-concrete culvert links is entered into on operation. Setting a plant for production of reinforce-concrete span beams.

- Survey operations:

Geodetic survey works are finished; a new executive survey has been completed; working drawings of the road 17 km, 2 bridge, 1 overpass, 1 agriculture machinery pass and 20 culverts are ready.

- Physical progress as:

| Year | Month | Plan of disbursement (tenge) | Physical progress (tenge) |  | Remarks |
| --- | --- | --- | --- | --- | --- |
| 2014 | December | 123 505 262,94 | 123 505 262,94 |  | IPC # 1 |
| 2015 | June | 124 773 558,55 | 124 773 558,55 |  | IPC # 2 |
|  | September | 79 730 062,85 | 79 730 062,85 |  | IPC # 3 |
|  | November | 152 836275,53 | 152 836 275,53 |  | IPC # 4 |
|  | December | 43 724 147,59 | 43 724 147,59 |  | IPC # 5 |
|  | Total as 2014-2015y | 524 569 307,46 | 524 569 307,46 |  | Including VAT |
| 2016 | January | 164 150 000 | 106 124 161,11 |  | IPC # 6 |
|  | February | 225 200 000 | 28 418 405, 41 |  | IPC # 7 |
|  | March | 594 460 000 | 21 875 097,63 |  | IPC # 8 |
|  | Total as 2014-2016г | 1 508 379 307,46 | 680 986 971,61 | 45,14 | Including VAT |

6. Financial progress as :

| Year | Month | Plan of disbursement | Financial progress |  | Remarks |
| --- | --- | --- | --- | --- | --- |
| 2014 | December | 123 505 262,99 | 123 505 262,99 |  | IPC # 1 |
| 2015 | June | 145 333 157,41 | 145 333 157,41 |  | IPC # 2 |
|  | September | 140 282 975,29 | 140 282 975,29 |  | IPC # 3 |
|  | November | 170 075 757,04 | 170 075 757,04 |  | IPC # 4 |
|  | December | 120 277 348,49 | 120 277 348,49 |  | IPC # 5 |
|  | Total as 2014-2015y | 699 474 501,21 | 699 474 501,21 |  | Including VAT |
| 2016 | January | 147 730 000 | 135 117 345,21 |  | IPC # 6 |
|  | February | 254 310 000 | 81 273 565, 72 |  | IPC # 7 |
|  | March | 548 490 000 | 150 251 887,11 |  | IPC # 8 |
|  | Total as 2014-2016y | 1 650 004 501,21 | 1 066 117 299,25 | 64,61 | Including VAT |

7. Interim Payment Certificates

| № | Period | Amount | Remark |
| --- | --- | --- | --- |
| 1 | 14.11.2014 | 123,505,262.99 | Paid |
| 2 | from 08.04.2015 till 08.06.2015 | 145,333,157.41 | Paid |
| 3 | from 08.06.2015 till 08.09.2015 | 140,282,975.29 | Paid |
| 4 | from 08.09.2015 till 25.11.2015 | 170 075 757,04 | Paid |
| 5 | from 26.11.2015 till 22.12.2015 | 120 277 348,49 | Paid |
| 6 | From 23.12.2015 till 27.01.2016 | 135 117 345, 21 | Paid |
| 7 | From 28.01.2016 till 01.03.2016 | 81 273 565, 72 | Paid |
| 8 | From 02.03.2016 till 15.03.2016 | 150 251 887,11 | Not paid |

- Information on executed works as of March:

| Works | Unit of measure | Plan | Actual | % of execution | Advancing/delay |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | quantity | days |
| Earthworks | th.m3 | 697,58 | 285,29 | 40,9 | -411,98 | -160 |
| Subgrade | km | 60 | 5,94 | 9,9 | -54,06 | -190 |
| Subbase | km | 60 | 3,40 | 5,66 | -56,40 | -190 |
| Crushed stone base | km | 60 | 1,61 | 2,68 | -58,39 | -190 |
| Cement concrete pavement | km | 51,34 | 0 | 0 | -51,34 | -150 |
| Culverts | nos | 96 | 6,5 | 6,77 | -89,5 | -180 |
| Cattle passes | nos | 3 | 1,5 | 50 | -1,5 | -90 |
| Bridges and overpasses | nos | 10 | 0,75 | 7,5 | -9,25 | -180 |
| Milling | km | 60 | 16,3 | 17,16 | -43,7 | -120 |

- Main road-construction materials procurement as of March:

| Material | Unit of measure | Plan | Actual | % of execution | Advancing / delay |
| --- | --- | --- | --- | --- | --- |
| Crushed stone | thous.m3 | 433,92 | 50,45 | 11,62 | -125 |
| Sand and gravel mix | thous.m3 | 566,9 | 124,0 | 21,87 | -120 |
| Sand | thous.m3 | 138,8 | 6,2 | 4,47 | -130 |
| Cement | thous.ton | 98,8 | 5,68 | 5,74 | -130 |
| Reinforced concrete goods | thous.m3 | 6,45 | 2,387 | 37 | -120 |

- Personnel mobilization:

| № | Personnel | Requirement for 2016 | Actual as of the current date | Among them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | Engineering and administrative personnel | 58 | 32 | 23 | 9 |
| 2 | Laboratory | 25 | 7 | 0 | 7 |
| 3 | Surveyors | 15 | 21 | 2 | 19 |
| 4 | Specialized machinery operators, damp drivers | 328 | 255 | 33 | 222 |
| 5 | Road workers | 310 | 143 | 62 | 81 |
| 6 | Others | 53 | 175 | 44 | 131 |
| TOTAL | 782 | 633 | 164 | 469 |

- Equipment mobilization:

| № | Equipment | Requirement for 2016 | Actual as of the current date | % | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Bulldozer | 4 | 3 | 75,0 |  |
| 2 | Excavator | 12 | 11 | 91,6 |  |
| 3 | Loader | 8 | 4 | 50,0 |  |
| 4 | Grader | 5 | 4 | 80 |  |
| 5 | Roller | 9 | 8 | 88,8 |  |
| 6 | Dump truck | 90 | 80 | 88,8 |  |
| 7 | Water tank | 6 | 3 | 50,0 |  |
| 8 | Asphalt paver | 2 | 1 | 50,0 |  |
| 9 | Concrete paver | 1 | 1 | 100,0 |  |
| 10 | Crane | 7 | 7 | 100,0 |  |
| 11 | Concrete batching plant | 2 | 2 | 100,0 |  |
| 12 | Crushing plant | 2 | 3 | 150,0 |  |
| 13 | Piling machine | 2 | 2 | 100,0 |  |
| 14 | Hauler | 2 | 2 | 100,0 |  |
| 15 | Concrete mixer | 5 | 3 | 60,00 |  |
| 16 | Light vehicles | 16 | 20 | 125 |  |
| 17 | Milling machine | 1 | 1 | 100,0 |  |
| 18 | Others | 61 | 55 | 90,1 |  |
| TOTAL | 235 | 210 | 89,36 |  |

- Subcontractors mobilization:

«Shyrak-LKS» LLP have started the works on communication lines relocation.

«KazTSEP» LLP have started the main works.

Road construction materials suppliers:

- “KAZH TAS” LLP – GSM, sand.

- Kunzhuek kurylys – crushed stone 5x20, crushed stone 20x40.

- Saipov IPC - crushed stone 0x40.

- Standart cement – cement.

Outstanding issues:

- The Contractor has a serious financial crisis on site as a result of that all work and planning go very slowly. The Project Manager does not receive funds from the main office Evrascon in Baku.

- Contractor provided very small material such as: crushed stone, sand and cement.

Progress of work

Beginning of works – on 8th of April, 2015.

- Milling - 16,3 km.

- Works on restoration of road pavement and subgrade are begun.

- Dismantling works on the overpass at PK 715 and Kokparsay bridge at PK 755 are finished.

- Dismantling works on the bridge Sary-Bulaksay at PK 864+68 are began, 40 beams of span structure are dismantled. Works on drilling of bored piles on the support No. 1 are finished. Works on drilling of bored piles on the support No. 2 are conducted.

- On the overpass at PK715 filling of a grillage with reinforcing on a support 1,2,3,4 and 5 is finished, filling of column of support on a support 1,2,4 and 5 (left) are completed, filling of columns on a support No. 3 are conducted.

- On the bridge at PK 755 hammering in a pile under support 1,2 and 3 is finished, works on the device of grillage No. 1 are finished, works on the device of grillage No. 3 are conducted.

- Works on the device of cattle passes on the PK 740+40 and the PK 846+30 from monolithic concrete are conducted. Backfilling is completed at PK 699+22, PK 702+93, PK 724+67, PK 731+70, PK 762+48, PK 799+27, PK 834+64. At PK 740+24, PK 869+90, PK829+50 it has been completed culvert links installation. At PK 858 the device of the base of support of the overpass under agricultural machinery passes is conducted. At PK 784+50 the base device under a culvert body is conducted. At PK 848 backfilling is conducted. At PK 815+91, PK 818+67, PK 789+34 development of excavation is conducting. Contractor has no intention to purchase reinforced concrete products for culverts and bridges as he started to produce them at his production base. Installation of beam workshop for reinforced concrete production of bridge structures has been completed. 12 beams L=21 m long are let out.

- Top soil removal – 13,5 km executed on the left side.

- Trees uprooting has been performed on 17,1 km.

- Connection to the main power supply line of production base is completed.

- Water supply works on the production base are completed by “Nur-AiKen Service” LLP. 350 m are drilled.

Resident Engineer					S. Irmanov