# Work progress information

Reconstruction project of international transit corridor, highway “Western Europe-Western China” km 1702-1752 (Lot No.7) in Kyzylorda region.

Length 49 km

# Contractor: JSC “EVRASCON”

# Engineer:  “Kazdorproject” Ltd.

New Contract amount:  8 233 648 569,50 KZT/тенге;

Disbursement – 3 407 166 037,78 KZT.

Including 5% advance for mobilization – 407 240 645 KZT.

Remainder of work – 4 826 482 531,72KZT;

Subcontractors: The contract concluded by general contractor with subcontractor on reconstruction of PL-35 kV with company JSC “KREK”, Kyzylorda.

The base at site PK196 (ACP, CCP and Laboratory).

Execution of work production schedule                                        June 29, 2015

| № | Description of work | Total on project | Fact from the beginning of construction | Remainder of work on 29.06. 2015 | Execution fact from beginning of the year | Delay/ advance from work program, in days | Executed % |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, km | 49 | 49,0 | 0,0 | 6,50 | 0 | 100% |
| 2 | Subbase, km | 49 | 49,0 | 0,0 | 6,59 | 0 | 100% |
| 3 | Lower layer base C-4, km | 49 | 49,0 | 0,0 | 7,57 | 0 | 100% |
| 4 | Upper layer base 12 cm, km | 49 | 48,3 | 0,7 | 7,10 | -8 | 99% |
| 5 | Binder course 10 cm, km | 49 | 44,6 | 4,4 | 3,43 | -51 | 91% |
| 6 | Wearing course CSMA, km | 49 | 0,0 | 49,0 | 0,0 | -60 | 0% |
| 7 | Culverts, pc. | 45 | 41,5 | 5,4 | 0,6 | -47 | 93% |
| 8 | Bridges, pc. | 13 | 10,5 | 2,5 | 0,6 | -15 | 79% |

Materials stockpiling:

| Materials stockpiling | Plan for 2015 | Fact on June 29, 2015 | Delay/ advance from work program, in days | Executed % |
| --- | --- | --- | --- | --- |
| 1 | Quarry stone for stockpiling of crushed stone thousand/ton | 258,623 | 58,390 | 0 |  |
| 2 | Crushed stone thousand/ ton |  | 52,815 | -41 | 59% |
| 3 | SGM thousand/ton | 240,250 | 90,354 | -61 | 60% |
| 4 | Sieve thousand/ ton | 54,080 | 30,155 | -28 | 76% |
| 5 | Bitumen thousand/ton | 8,105 | 1,983 | -38 | 62% |

# Technique quantity, which is necessary for execution of work plan for 2015

| Name | Need for June 2015 | As of June 29, 2015 |
| --- | --- | --- |
|  |  | The fact is on site on June 29, 2015 | Additionally required |
| Бульдозер / Bulldozer | 3 | 2 | 1 |
| Экскаватор / Excavator | 9 | 4 | 5 |
| АВЗ/ ACP | 2 | 1 | 1 |
| Бетонный завод/ Concrete plant | 1 | 1 |  |
| ДСУ/RCA | 2 | 2 |  |
| Погрузчик / Loader | 10 | 5 | 5 |
| Автогрейдер / Grader | 4 | 3 | 1 |
| Фреза / Milling machine | 1 | 0 |  |
| Катки / Rollers | 7 | 7 |  |
| Асфальтовый каток/Asphalt compactor | 10 | 7 | 3 |
| Асфальтоукладчик / Asphalt paver | 5 | 3 | 2 |
| Автосамосвалы / Dump trucks | 107 | 109 |  |
| Автогудронатор / Bitumen distributor | 1 | 1 |  |
| Битумовоз / Bitumen truck | 4 | 3 | 1 |
| Поливочная машина / Water truck | 6 | 3 | 3 |
| Бензовоз / Gas tank truck | 2 | 2 |  |
| Кран / Crane | 3 | 1 | 2 |
| тралл / Trailer | 1 | 1 |  |
| миксеры для бетона / Concrete mixer | 4 | 4 |  |
| Цементовоз/Cement truck | 2 | 1 | 1 |
| Разметочная машина / Measuring machine | 0 | 0 |  |
| Total/Всего | 184 | 161 | 23 |

# Personnel:

| Personnel | Lot No.7 |
| --- | --- |
|  | Plan | Fact |
| Total personnel for June 2015. | 388 | 422 |

# The following works are being held at the moment:

# Embankment filling of subgrade at the ramps PK 163+85, PK 178+11, PK206+78;

# Site inspection before CSMA paving PK 0+00-PK50+00;

# Binding course construction of 12 cm PK 434+60-PK442+00

# Handrails installation at bridge No. 12 PK 459+85;

# Reinforcing of beams at overpass PK 196+53.02.

# Issues of concern and causes that have arisen at this section

- Partial damage of mobilized road-building equipment and machinery and equipment of ACP.

- Insufficient quantity of qualiffied personnel

- Partial lack of SGM

- There is not concluded contract on delivery of geogrid, biological material, mineral powder.

- The issue under Road-building material of previous Contractor “Impresa” is not solved

- Lack of money to implement work