INFORMATION

South-West Road Project Western Europe – Western China 1980+000-2012+000 (13 lot)  Kyzylorda Oblast

length - 32 km.

Contractor:  SPA«Todini Construzioni Generali»

Engineer: LTD “Rougton International”

Subcontractors: LLP Stroimost 2010 – for bridge and culvert construction.

Laboratory.

The laboratory is located in Zhanakorgan and equipped fully for 100%.

Plan for 2012   - prepared                                                                                         December 2012

| № | Work description | Total in contract | Executed in 2010-2011 | Plan for 2013 | Actual from the beginning of the year | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, cum | 2299 | 2221 | 77,5 | 77,5 | 100 |  |
| 2 | Sub base layer, km | 64 | 63.76 | 0.2 | 0.2 | 100 |  |
| 3 | Base course С-4, km | 64 | 63,76 | 0.2 | 0.2 | 100 |  |
| 4 | Wearing course, km | 64 | 63.58 | 0.4 | 0,42 | 100 |  |
| 5 | Lower layer, km | 64 | 61,69 | 2.3 | 2,3 | 100 |  |
| 6 | Top layer SMA, km | 64 | 0 | 64 | 64 | 100 |  |
| 7 | Overpass, no | 1 | 0,43 | 0,57 | 0,56 | 98 |  |
| 8 | Pipe culverts, no | 19 | 19 | 0 | 0 | 100 |  |

| Preparation of material |  | Total in contract | Plan for 2012 | actual | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thousand./ton | 606,11 | 67,81 | 67,81 | 100 |  |
| 2 | SGM thousand./ton | 422,8 | 0 | 0 |  |  |
| 3 | Reinforced concrete elements cum3 | 2,7 | 0,20 | 0,20 | 100 |  |
| 4 | Bitumen thousand./ton | 21,3 | 4,6 | 4,6 | 100 |  |
| 6 | Cellulose additions for SMA | 0,303 | 0,303 | 0,27 | 100 |  |

Item of equipment needed for execution of programme in 2012

| Name | Needed | To December 2012 |  |
| --- | --- | --- | --- |
|  |  | Actual at site | Additional needed |
| Dozer |  | 2 |  |
| Excavator | 4 | 1 |  |
| Loader | 2 | 6 |  |
| Paver | 9 | 9 |  |
| Grader | 3 | 2 |  |
| Dump trucks | 35 | 35 |  |
| Asphalt paver | 2 | 4 |  |
| Asphalt concrete plant | 1 | 1 |  |
| Cement concrete plant | 1 | 1 |  |
| Road repair-construction site | 1 | 1 |  |
| Other | 25 | 25 |  |
| Total | 84 | 87 |  |