INFORMATION

Reconstruction Project of International Transit Corridor of roads «Western Europe-Western China» km км 1947+000-1980+000 (LOT 12) in Kyzylorda oblast

Length 32 км.

Contractor:  S.p.А. «Todini Construzioni Generali»

Engineer: LTD “Rougton International”

Subcontractors:

1) LLP «Stroi Most-2010» bridge works.

Laboratory.

The laboratory is located in Zhanakorgan village, equipped for 100%.

Schedule execution of work productivity (Plan for 2012.)                        December 2012

| № | Description of works | Overall in contract | Done 2010-2011г | Plan for 2012 | Actual from the beginning of the year | Done, % | Delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, thousand .м3 | 1159 | 1370 | 43,228 | 43,228 | 100 |  |
| 2 | Sub base layer, км | 64 | 59,92 | 4,1 | 4,08 | 100 |  |
| 3 | Base course С-4, km | 64 | 58,61 | 5,4 | 4,93 | 99 |  |
| 4 | Wearing course, km | 64 | 58,48 | 5,5 | 5.05 | 99 |  |
| 5 | Lower layer, km | 64 | 52,82 | 11,2 | 10.54 | 99 |  |
| 6 | Top layer SMA, km | 64 | 1,39 | 62,6 | 59.79 | 96 |  |
| 7 | Bridges, no | 4 | 2,18 | 1,82 | 1,78 | 99 |  |
| 8 | Pipe culverts, no | 14 | 13,5 | 0,5 | 0 | 100 |  |

| Preparation of material |  | Total in contract | Plan for 2012 | actual | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thousand./ton | 617,483 | 56,3 | 56,38 | 100 |  |
| 2 | SGM thousand./ton | 416,5 | 1,6 | 1,6 | 100 |  |
| 3 | Reinforced concrete elements cum3 | 3,506 | 1,00 | 1,00 | 100 |  |
| 4 | Bitumen thousand./ton | 19,481 | 4,3 | 4,3 | 100 |  |
| 6 | Cellulose additions for SMA | 0,297 | 0,297 | 0,297 | 100 |  |

Item of equipment needed for execution of programme in 2012

| Name | Needed | In December 2012 |  |
| --- | --- | --- | --- |
|  |  | Actual at site | Additional needed |
| Dozer |  | 2 |  |
| Excavator | 4 | 4 |  |
| Loader | 2 | 4 |  |
| Paver |  | 3 |  |
| Grader | 3 | 3 |  |
| Dump trucks | 35 | 21 |  |
| Asphalt paver | 2 | 3 |  |
| Asphalt concrete plant | 2 | 2 |  |
| Cement concrete plant | 1 | 1 |  |
| Road repair-construction site | 1 | 1 |  |
| Other | 25 | 25 |  |
| Total | 80 | 88 |  |