INFORMATION

South-West Road Project Western Europe – Western China 1917+000-1947+000 (11 lot)  Kyzylorda Oblast

length - 29 km.

Подрядчик:  С.п.А. «Todini Construzioni Generali»

Инженер:LTD “Rougton International”

Subcontractors: LLP Stroimost 2010 – for bridge and culvert construction.

Laboratory.

The laboratory is located in Zhanakorgan and equipped fully for 100%.

Plan for 2012   - prepared 07.12.2012

| № | Work description | Total in contract | Executed in 2010-2011 | Plan for 2013 | Actual from the beginning of the year | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, cum | 2161,48 | 1781,66 | 396,68 | 396.66 | 100 |  |
| 2 | Sub base layer, km | 58 | 44,12 | 13,9 | 13.7 | 99,50 |  |
| 3 | Base course С-4, km | 58 | 33,84 | 24,2 | 22.73 | 97,53 |  |
| 4 | Wearing course, km | 58 | 32,19 | 25,8 | 23.62 | 96,22 |  |
| 5 | Lower layer, km | 58 | 29,85 | 28,2 | 24.2 | 92 |  |
| 6 | Top layer SMA, km | 58 | 0,00 | 58 | 5,10 | 8,79 |  |
| 7 | Overpass, no | 2 | 1,01 | 0,99 | 1,76 | 88 |  |
| 8 | Pipe culverts, no | 36 | 32 | 4 | 4 | 100 |  |

| Preparation of material |  | Total in contract | Plan for 2012 | actual | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thousand./ton | 606,11 | 67,81 | 67,81 | 100 |  |
| 2 | SGM thousand./ton | 422,8 | 0 | 0 |  |  |
| 3 | Reinforced concrete elements cum3 | 2,7 | 0,20 | 0,20 | 100 |  |
| 4 | Bitumen thousand./ton | 21,3 | 4,6 | 4,6 | 100 |  |
| 6 | Cellulose additions for SMA | 0,303 | 0,303 | 0,27 | 100 |  |

Item of equipment needed for execution of programme in 2012

| Name | Needed | To December 2012 |  |
| --- | --- | --- | --- |
|  |  | Actual at site | Additional needed |
| Dozer | - | 2 |  |
| Excavator | 4 | 4 |  |
| Loader | 2 | 4 |  |
| Paver | - | 5 |  |
| Grader | 3 | 3 |  |
| Dump trucks | - | 21 |  |
| Asphalt paver | 2 | 3 |  |
| Asphalt concrete plant | 1 | 1 |  |
| Cement concrete plant | 1 | 1 |  |
| Road repair-construction site | 1 | 1 |  |
| Other | 2 | 5 |  |
| Total | 16 | 50 |  |