INFORMATION

South-West Road Project Western Europe – Western China 2012+000-2057+000 (14 lot)  Kyzylorda Oblast

length - 45 км.

Contractor:  С.п.А. «Todini Construzioni Generali»

Engineer:LTD “Rougton International”

Subcontractor: «Sine Midas Stroi», executes all types of works at KM 2012+000-2057+000

Laboratory.

The laboratory is located in Zhanakorgan and equipped fully.

Plan for 2012   - prepared                                                                            December 2012

| № | Work description | Total in contract | Executed in 2010-2011 | Plan for 2012 | Actual from the beginning of the year | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks, cum | 1280,32 | 1247 | 33.290 | 33.29 | 100 |  |
| 2 | Subbase layer, km | 88,6 | 86,09 | 2.5 | 2,54 | 100 |  |
| 3 | Base course С-4, km | 88,6 | 68,25 | 20,04 | 18.78 | 98 |  |
| 4 | Wearing course, km | 88,6 | 66 | 22,6 | 21.34 | 98 |  |
| 5 | Lower layer, km | 88,6 | 63,6 | 25,0 | 23.74 | 98 |  |
| 6 | Top layer SMA, km | 88,6 | 0 | 88,6 | 87.34 | 98 |  |
| 7 | Bridge, no | 1 | 0 | 1 | 0,70 | 70 |  |
| 8 | Pipe culverts, no | 29 | 24 | 5 |  | 83 |  |

| Preparation of material |  | Total in contract | Plan for 2012 | actual 07.12.2012 | executed.% | delay(+,-) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone thousand./ton | 1150 | 281,65 | 281,65 | 100 |  |
| 2 | SGM thousand./ton | 1258,32 | 49,8 | 49,8 | 100 |  |
| 3 | Reinforced concrete elements cum3 | 1,93 | 0,5 | 0,5 | 100 |  |
| 4 | Bitumen thousand./ton | 25.7 | 12,58 | 12.58 | 100 |  |
| 6 | Cellulose additions for SMA | 0.408 | 0.408 | 0.35 | 86 |  |

Item of equipment needed for execution of programme in 2012

| Name | Needed | To December 2012 |  |
| --- | --- | --- | --- |
|  |  | Actual at site | Additional needed |
| Dozer |  |  |  |
| Excavator | 4 | 5 |  |
| Loader | 2 | 4 |  |
| Paver | 10 | 12 |  |
| Grader | 3 | 2 |  |
| Dump trucks |  | 48 |  |
| Asphalt paver | 1 | 1 |  |
| Asphalt concrete plant | 1 | 1 |  |
| Cement concrete plant | 1 | 0 |  |
| Road repair-construction site | 1 | 2 |  |
| Other | 15 | 16 |  |
| Total |  | 91 |  |