Information on performed work

Project of International Transit Corridor Reconstruction,

Road “Western China-Western Europe” km 1837-1877 (Lot 9) in Kyzylorda Oblast

Lenth – 40 km

General Contractor: “TODINI” JSC

Engineer: Dongsung Engineering Co. Ltd.

Execution of work program (Plan for 2012)                30 November 2012

At present, the progress of work related to the current work plan in the following quantities:

| №. | Work description | Total Contract | Achieved in 2010-2011 | Plan for 2012 | Actual | Actual in 2012 (%) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthwork, Thos. (m3) | 1,442.97 | 1,419.99 | 22.98 | 15.98 | 70% |
| 2 | Granular sub-base Н=20 cm, (km) | 80.0 | 78.1 | 1.9 | 1.6 | 84% |
| 3 | Crushed stone base С4, Н=18 cm, (km) | 80.0 | 78.0 | 2.0 | 1.7 | 85% |
| 4 | Porous Asphalt, Н=12 cm, (km) | 80.0 | 77.9 | 2.1 | 1.0 | 48% |
| 5 | Binder course Н=10 cm, (km) | 80.0 | 77.4 | 2.6 | 0.6 | 23% |
| 6 | SMA wearing course, H=5 cm, (km) | 80.0 | 0 | 80.0 | 50.0 | 63% |
| 7 | Bridges, (No.) | 2 | 0.3 | 1.7 | 1.4 | 82% |
| 8 | Culverts, (No.) | 16 | 16 | - | - | - |

Material procurement

| № | Material procurement | Unit | Plan for 2012 | Plan for the current date | Procured actually in quarry |  | Including in storage at construction site | Work leading or delay |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | quantity |  | quantity | % | quantity |  |
| 1 | SGM for granular subbase | tn | 14,000 | 14,000 | 14,000 | 100 | 10,000 | 0 |
| 2 | CSSM for crushed stone base | tn | 9,865 | 9,865 | 9,865 | 100 | 9,865 | 0 |
| 3 | For shoulder strengthening and dividing strip С-6 | tn | 97,484.8 | 97,484,8 | 97,484.8 | 100 | 97,484.8 | 0 |
| 4 | For roadsides strengthening, crushed stone fr. 20-40 | tn | 5,200 | 5,200 | 2,000 | 38 | 2,000 | -3,200 |
| 5 | For asphalt concrete |  |  |  |  |  |  |  |
|  | Bitumen | tn | 7,620 | 7,620 | 5,200 | 68 | 640 | -2,420 |
|  | Screening | tn | 33,380 | 33,380 | 33,380 | 100 | 9,870 | 0 |
|  | Crushed stone | tn | 84,176 | 84,176 | 107,368 | 127 | 43,800 | 0 |
|  | Mineral fines | tn | 9,953 | 9,953 | 10,416 | 105 | 1,645 | -6,653 |
|  | Cellulosic admixture | tn | 370 | 370 | 300 | 80 | 40 | -90 |
| 6 | Reinforced concrete goods for pipes | m³ | 660 | 660 | 660 | 100 | 60 | -34 |
| 7 | Reinforced concrete goods for bridges | m³ | 930 | 930 | 930 | 100 | 0 | 0 |
| 8 | Transport barrier | m | 40,124 | 40,124 | 40,124 | 100 | 40,124 | 0 |

Mobilization of equipment on Lot 9

| No. | Equipment | Lot 9 |  |
| --- | --- | --- | --- |
|  |  | Plan | Actual |
| 1 | Road construction machinery | 60 | 25 |
| 2 | Bulldozer | 1 | 2 |
| 3 | Excavator | 1 | 2 |
| 4 | Loader | 1 | 1 |
| 5 | Roller | 9 | 2 |
| 6 | Grader | 2 | 1 |
| 7 | Dump truck | 35 | 10 |
| 8 | Asphalt paver | 4 | 0 |
| 9 | Crane | 2 | 1 |
| 10 | Other | 5 | 6 |
| 11 | Asphalt batch plant | 2 | 2 |
| 12 | Mill for mineral fines production | 1 | 1 |
| 13 | Bitumen base | 1 | 1 |
| 14 | Dead-end track | 2 | 2 |
| 15 | Laboratory | 1 | 100% |
| 16 | Concrete batching plant | 1 | 1 |