INFORMATION

Road reconstruction project of International Transit Corridor “WE-WC” km 1877-1917 (Lot 10) in Kyzylorda

The length is 40,471  km.

Contractor:  “Todini” Costruzioni Generali S.p.A.

Engineer:     Dongsung Engineering Co., Ltd

• The work progress schedule performance (plan for 2012) 04.12.2012.

| No. | Work name | Total Contract | Achieved in 2010-2011 | Plan for 2012 | Actual up to Nov 30 2012 | Actual in 2012 (%) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthwork, Thos. (m3) | 1,383.32 | 774.37 | 608.95 | 486.70 | 80% |
| 2 | Granular sub-base Н=20 cm, (km) | 81.0 | 34.02 | 46.98 | 28.47 | 61% |
| 3 | Crushed stone base С4, Н=18 cm, (km) | 81.0 | 30.19 | 50.81 | 28.69 | 56% |
| 4 | Porous Asphalt, Н=12 cm, (km) | 81.0 | 29.25 | 51.75 | 25.63 | 50% |
| 5 | Binder course Н=10 cm, (km) | 81.0 | 28.92 | 52.08 | 21.20 | 41% |
| 6 | SMA wearing course, H=5 cm, (km) | 81.0 | 0 | 0 | 0 | - |
| 7 | Bridges, (No.) | 3 | 0.5 | 2.5 | 1.0 | 40% |
| 8 | Culverts, (No.) | 25 | 14 | 11 | 9 | 82% |

Materials procurement

| No | Material procurement | Unit | Plan for 2012 | Plan for the current date | Procured actually in quarry |  | Including in storage at construction site | Work leading or delay |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | quantity | 30.11.12 | quantity | % | quantity | quantity |
| 1 | For granular subbase SGM | t | 426,100 | 426,100 | 373,000 | 70,0 | 373,000 | - 53,100 |
| 2 | Crushed stone base | t | 195,800 | 195,800 | 191,800 | 97,0 | 191,800 | - 4,000 |
| 3 | Geosynthetic materials | m² | 693,430 | 693,430 | 553,400 | 79,0 | 553,400 | - 140,030 |
| 4 | Asphalt concrete |  |  |  |  |  |  |  |
|  | Bitumen | t | 18,000 | 18,000 | 10,000 | 55,0 | 10,000 | -8,000 |
|  | Screening | t | 165,170 | 165,170 | 85,000 | 51,0 | 85,000 | - 80,170 |
|  | Crushed stone | t | 221,080 | 221,080 | 131,350 | 59,0 | 131,350 | - 89,730 |
| 5 | Concrete goods for pipes | m³ | 1,510 | 1,510 | 1,510 | 100 | 1,510 | 0 |

Equipment`s quantity necessary for performing the work program for 2012.

| Name | Necessity |  |  |  |
| --- | --- | --- | --- | --- |
|  |  | Mobilized at the site in 2012 | Remaining from the plan | Actual worked on the site 17.09.2012 |
| Bulldozer | 1 | 2 | +2 | 2 |
| Excavator | 1 | 1 | 0 | 2 |
| Loader | 1 | 2 | 0 |  |
| Roller | 9 | 8 | 0 | 1 |
| Grader | 2 | 2 | 0 | 1 |
| Dump truck | 35 | 25 | -10 |  |
| Paver | 4 | 2 | 0 |  |
| Asphalt Plant | 2 | 2 | 0 | 1 |
| Crane | 2 | 2 |  |  |
| Concrete plant | 1 | 1 | 0 |  |
| Crushing screening plant | 2 | 2 | 0 |  |
| Others | 20 | 17 | 0 |  |
| Total | 78 | 64 | -8 | 7 |