INFORMATION

East-West Roads Project Western Europe-Western China International Transit Corridor (CAREC 1B), Reconstruction (construction) of road “ALMATY-KOKPEK-CHUNJA-KOKTAL-KHORGOS”

- Contract – EWRP-Bridges and overpasses on lot V and VI -ICB(W)-001/2013

- Contractor –JV “Evrascon & MO-1”

- Contract amount – 6 803 041 924 tg

- Construction period– 30 month

Commencement date: 11th October 2013

Time for completion: 10th April 2016

- Money developed up to 2015 - 2 220 586 800,02 tg

- Money development plan for 2015– 3 874 133 000 tg

- Consultant Engineer– «Dongsung Engineering/Dongmyeng Engineering» / «Zhol-Sapa»LLP

- Design Company – “Kazakhstan zholdary”

23.04.2015

- Main indicators

Total: 30 bridges & Khorgos dam protection

| Description | Quantity | Description | Quantity |
| --- | --- | --- | --- |
| Bridges | 14 | Overpasses | 3 |
| Cattle crosses | 9 | Interchanges | 4 |

- Details of works performance according to schedule:

| № | Description | Evrascon | MO-1 | Total |
| --- | --- | --- | --- | --- |
| 1 | Bridges | Started | 10 | 8 | 20 |
|  |  | On progress | (5) | (3) | (8) |
|  |  | Remained | 8 | 4 | 10 |
|  |  | Total | 18 | 12 | 30 |
| 2 | Dam protection | Retaining wall | - | 110 m | 144 m/220 m |
|  |  | Sheet piles | - | 70 m | 70 m/70 m |
|  |  | Slope protection | - | 0 m | 144 m/805 m |

  - Progress

| № | Description | Total on Contract | Developed in 2013-2014 | Plan for 2015 (mln. tg) |
| --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date | % |
| 1. | Physical progress on bridges, un. | 6,074 | 2,531 | 4,016 | 537 | 13 |
| 2. | Monetary progress, tg | 6 803 | 2 220 | 3 874 | 384 | 10 |

  - Bridge works

| № | Works description | Total on contract | Performed in 2013-2014г | 2015 | % |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date |  |
| 1 | Earthworks, m3 | 256 573 | 11 139 | 245 434 | 1954,6 | 3,2 |
| 2 | Pile driving, m3 | 5 460 | 2 518 | 2 942 | 200 | 7 |
| 3 | Installation of foundation, m3 | 14 272 | 4 433 | 9 839 | 1842 | 19 |
| 4 | Installation of columns and cross bars (wall) | 10 896 | 2 544 | 8 352 | 442,58 | 5 |
| 5 | Installation of rubber bearings | 3 432 | 140 | 3 292 | 170 | 5 |
| 6 | Installation of span slabs, un. | 968 | 106 | 862 | 52 | 6 |
| 7 | Installation of span beams, un. | 572 | 20 | 552 | 20 | 4 |
| 8 | Installation of handrails | 3 024 | 0 | 3 024 | 0 | 0 |
| 9 | Installation of guard rails | 11 064 | 0 | 11 064 | 0 | 0 |

- Materials procurement for 2015:

| № | Description | Total on contract | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of date | % |  |
| 1. | Aggregate,thous. m3 | 50,9 | 28,9 | 7,5 | 26 | “Dostar-S” |
| 2. | Sand, thous. m3 | 14,9 | 6,8 | 2,2 | 33 | “Dostar-S” |
| 3. | Sand (mixed), thous. m3 | 21,7 | 11,2 | 2,9 | 26 | “Dostar-S” |
| 4. | Cement, thous. m3 | 30,5 | 18,0 | 2,3 | 11 | “Bukhtarma” |
| 5. | Concrete products, thous. m3 | 26,6 | 16,0 | 3,42 | 20 | Production base of Evrascon/MO-1 |
| 6. | Re-bar and embedded parts, ton | 3 767 | 3 157 | 1052,1 | 33 | “Mechel” |

- Staff mobilization:

| № | Description | Requirement for 2015 | As of date |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | Engineers | 65 | 62 | 21 | 41 |
| 2 | Lab. | 10 | 7 | 2 | 5 |
| 3 | Survey | 10 | 7 | 3 | 4 |
| 4 | Operators | 60 | 50 | 10 | 40 |
| 5 | Dump trucks drivers | 70 | 66 | 1 | 65 |
| 6 | Labors | 200 | 92 | 25 | 67 |
| 7 | Assembler, mounters | 70 | 34 | 4 | 30 |
| 8 | Others | 100 | 39 | 4 | 35 |
| Total | 585 | 357 | 70 | 287 |

- Equipment mobilization:

| № | Description | Requirement for 2015 | As of date | JV “Evrascon&MO-1” |
| --- | --- | --- | --- | --- |
|  |  |  |  | Evrascon | МО-1 |
| 1 | Dozer | 5 | 3 | 1 | 2 |
| 2 | Excavator | 5 | 3 | 2 | 1 |
| 3 | Loader | 5 | 2 | 1 | 1 |
| 4 | Grader | 3 | 1 | 1 | 0 |
| 5 | Roller | 5 | 3 | 2 | 1 |
| 6 | Dump trucks | 15 | 12 | 8 | 4 |
| 7 | Water tank | 3 | 2 | 2 | 0 |
| 8 | Asphalt paver | 2 | 0 | 0 | 0 |
| 9 | Crane | 10 | 8 | 4 | 4 |
| 10 | Cement concrete plant | 3 | 3 | 1 | 2 |
| 11 | Pile driver | 5 | 3 | 3 | 0 |
| 12 | Trail | 5 | 2 | 1 | 1 |
| 13 | Mixer | 10 | 5 | 2 | 3 |
| 14 | Vehicles | 25 | 19 | 10 | 9 |
| 15 | Other | 10 | 10 | 10 | 0 |
| Total | 111 | 77 | 48 | 29 |

- Issues

1. Installation of dike between railway bridge and bridge

2. Absence of pile refusal at Pk 272, Pk 334, Pk 372

3. Absence of agreed elevation points of longitudinal profile Pk 233

4. Schedule delay