INFORMATION                                                As of 30.03.2016

Under the Project implementation of International Transit Corridor 
Western Europe -Western China, in Almaty region

By “OHL ZS” JSC Lot 8

- Contract: EWRP – Ili bridge (km 283) –ICB(W)-001/2013

- General Contractor: «OHL ZS»(Czech Republic)

- Contract amount: 6 394 053 055 tenge (Amount after variation 6 134 652 965.52 tenge)

- Construction period: 30 months (900 calendar days)

Commencement date: 4 October 2013

Completion date:  3 April 2016

- Disbursed until 2016: 5 442 047 568.22 tenge

- Plan for disbursement for 2016: 657 284 246.31 tenge (without taking into account variation orders)

- Engineer CSC: DongSung Engineering Co. Ltd/Dong Myeong Enginering Consultants and Architecture Co. Ltd./ “Zhol Sapa” LLP

- Designer: “Kazakhstan zholdary” JSC

As-built documentation:

Number of issued for week:		instructions: 0; letters: 0

Deadline for work program and Quality control plan submission: 3 April 2016

- Main indicators

Total number of artificial structures: 1-bridge over Ili river

| Name | Quantity | Name | Quantity |
| --- | --- | --- | --- |
| Bridges | 1 | Overpasses | 0 |
| Cattlepasses | 0 | Interchanges | 0 |

  - Bridge works

| № | Work description | Total under Contract | Performed until 2016 | 2016 |
| --- | --- | --- | --- | --- |
|  |  |  |  | Plan | Fact | % |
| 1 | Site clearance, m2 | 100 | 50 | 50 | 0 | 0 |
| 2 | Base course from crushed stone, m3 | 2 750 | 2 343 | 407 | 0 | 0 |
| 3 | Construction of piles, m3 | 9 034 | 9 034 | 0 | 0 | 0 |
| 4 | Construction of foundations, m3 | 4 857 | 4 857 | 0,015 | 0,015 | 100 |
| 5 | Construction of the body of pier), m3 | 1 822 | 1 822 | 0 | 0 | 0 |
| 6 | Reinforcing (tons) | 1 363 | 1 357,6 | 5,4 | 5,4 | 100 |
| 7 | Assembly of steel superstructures, ton | 3 222 | 3 222 | 0 | 0 | 100 |
| 8 | Installation of handrails | 2 768 | 1 384 | 1 384 | 0 | 0 |
| 9 | Installation of guard rails | 2 800 | 0 | 2 800 | 1 360 | 49 |
| 10 | Precast reinforced concrete plates at places of bridge connection (m3) | 183 | 177 | 6 | 0 | 0 |
| 11 | In-situ reinforced concrete strengthening of slopes of class B20 F200 (m3) | 1 028 | 386 | 642 | 203 | 32 |
| 12 | Painting works of metal span (m2) | 52 966 | 21 556 | 29 446 | 0 | 0 |
| 13 | Waterproofing of bridge deck (m2) | 16 942 | 10 185 | 6 757 | 0 | 0 |
| 14 | Pavement works with appplication of bitumen n(m3) | 1 636 | 490 | 1 146 | 0 | 0 |

- Material procurement for 2016:

| № | Description | Total | 2016 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of 08.09.2015 | % |  |
| 1. | Crushed stone m3 | 17,68 | 1,142 | 0,162 | 14 | “Dostar S” LLP |
| 2. | Sand m3 | 8,21 | 0,323 | 0,117 | 36 | “Sunkar” LLP |
| 3. | Sand gravel mix m3 | 14,64 | 0,655 | 0,546 | 83 | “Aluan A” LLP |
| 4. | Cement thous. tons | 7,10 | 0,280 | 0,226 | 80 | “Standard” LLP |
| 5. | Reinforced concrete products m3 | 0,224 | 0,224 | 0,172 | 76 | Production base of “MO-25” LLP |
| 6. | Re-bar and embedded parts, ton | 1,36 | 0,9 | 0,017 | 18 | “Modul” LLP |

- Personnel mobilization:

| № | Description | Requirement for 2016 | As of current date | Including: |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign | Local |
| 1 | TED | 25 | 25 | 7 | 18 |
| 2 | Laboratory | 5 | 5 | 1 | 4 |
| 3 | Survey | 2 | 2 | 0 | 2 |
| 4 | Operators | 36 | 36 | 0 | 36 |
| 5 | Truck drivers | 8 | 22 | 0 | 22 |
| 6 | Laborers | 90 | 55 | 0 | 55 |
| 7 | Others | 6 | 6 | 0 | 6 |
| Total | 172 | 151 | 8 | 143 |

- Equipment mobilization:

| № | Description | Requirement for 2016 | As of current date | OHL ZS JSC |
| --- | --- | --- | --- | --- |
|  |  |  |  | Contractor | Subcontractor |
| 1 | Bulldozer | 1 | 1 | - | 1 |
| 2 | Excavator | 1 | 1 | - | 1 |
| 3 | Loader | 1 | 1 | - | 1 |
| 4 | Auto grader | 0 | 0 | - | 0 |
| 5 | Rollers | 5 | 1 | - | 1 |
| 6 | Dump trucks | 2 | 1 | - | 1 |
| 7 | Water truck | 1 | 1 | - | 1 |
| 8 | Asphalt paver | 2 | 0 | - | 0 |
| 9 | Crane | 2 | 1 | - | 1 |
| 10 | Cement Concrete plant | 1 | 1 | - | 1 |
| 11 | Pile driver | 0 | 0 | - | 0 |
| 12 | Creeper | 1 | 1 | - | 1 |
| 13 | Concrete mixer | 2 | 1 | - | 1 |
| 14 | Vehicle | 1 | 5 | 4 | 1 |
| 15 | Others | 14 | 14 | - | 14 |
| Total | 34 | 29 | 4 | 25 |

- Maintenance

| Name | Under TOR /Contract | Actual |
| --- | --- | --- |
| Flats | 10 | 10 |
| Vehicles | 3 | 3 |
| Office | 1 | 1 |
| Work wear | 10 | 10 |

- Issues of concern:

| Content of issue | Ways of solving |
| --- | --- |
| 1.Existing bridge (needs repair) Variation Order №-4 | Without comment and without increase of approved amount.(with time extention) |
| 2.Variation Order №-2 | 2. Checked, sent for approval. |
| 3.Variation Order №-3 | 3.Comments under volume calculation |