INFORMATION

East-West Roads Project Western Europe-Western China International Transit Corridor (CAREC 1B), Reconstruction (construction) of road “ALMATY-KOKPEK-CHUNJA-KOKTAL-KHORGOS”

- Contract – EWRP-Bridges and overpasses on lot V and VI -ICB(W)-001/2013

- Contractor –JV “Evrascon & MO-1”

- Contract amount – 6 803 041 924 tg

- Construction period– 30 month

Commencement date: 11th October 2013

Time for completion: 10th April 2016

- Money developed up to 2014 - 2 220 586 800,02 tg

- Money development plan for 2015– 3 874 133 000 tg

- Consultant Engineer– «Dongsung Engineering/Dongmyeng Engineering» / «Zhol-Sapa»LLP

- Design Company – “Kazakhstan zholdary”

- Main indicators

Total: 30 bridges & Khorgos dam protection

| Description | Quantity | Description | Quantity |
| --- | --- | --- | --- |
| Bridges | 14 | Overpasses | 3 |
| Cattle crosses | 9 | Interchanges | 4 |

- Progress

2.1 Rate of progress

| № | Description | Total on Contract | Developed in 2013-2014 | Plan for 01.06.2015 (mln. tg) | Performed according to Contract |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date | % | Sum | % |
| 1. | Physical progress on bridges, un. | 6 074 | 805 | 1 512 | 396 | 26 | 1 201 | 20 |
| 2. | Monetary progress, tg | 6 803 | 2 220 | 1 270 | 557 | 44 | 2 757 | 40,5 |

2.2 Main works progress

| № | Description | Evrascon | MO-1 | Total |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Bridges | Started | 11 | 10 | 21 |  |
|  |  | On progress | 8 | 7 | (14) |  |
|  |  | Suspended | 3 | 3 | (7) |  |
|  |  | Remained | 7 | 2 | 9 |  |
|  |  | Total | 18 | 12 | 30 |  |
| 2 | Dam protection | Retaining wall | - | 216 m | 216 m/220 m | 99 |
|  |  | Sheet piles | - | 70 m | 70 m/70 m | 100 |
|  |  | Slope protection | - | 103 m | 103 m/805 m | 10 |

2.3 Bridge works

| № | Works description | Total on contract | Performed in 2013-2014г | 2015 | Total work done |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Plan | As of date | % |  |
| 1 | Earthworks, m3 | 256 573 | 11 139 | 245 434 | 4233,8 | 6,9 | 6 |
| 2 | Pile driving, m3 | 5 460 | 2 518 | 2 942 | 987 | 34 | 64 |
| 3 | Installation of foundation, m3 | 14 272 | 4 433 | 9 839 | 2244 | 23 | 47 |
| 4 | Installation of columns and cross bars (wall) | 10 896 | 2 544 | 8 352 | 992 | 12 | 32 |
| 5 | Installation of rubber bearings | 3 432 | 140 | 3 292 | 170 | 5 | 9 |
| 6 | Installation of span slabs, un. | 968 | 106 | 862 | 52 | 6 | 16 |
| 7 | Installation of span beams, un. | 572 | 20 | 552 | 20 | 4 | 7 |
| 8 | Installation of handrails | 3 024 | 0 | 3 024 | 0 | 0 | 0 |
| 9 | Installation of guard rails | 11 064 | 0 | 11 064 | 0 | 0 | 0 |

- Materials procurement for 2015:

| № | Description | Total on contract | 2015 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | As of date | % |  |
| 1. | Aggregate,thous. m3 | 50,9 | 28,9 | 12,0 | 42 | “Dostar-S” |
| 2. | Sand, thous. m3 | 14,9 | 6,8 | 4,0 | 58 | “Dostar-S” |
| 3. | Sand (mixed), thous. m3 | 21,7 | 11,2 | 4,9 | 43 | “Dostar-S” |
| 4. | Cement, thous. m3 | 30,5 | 18,0 | 2,9 | 16 | “Bukhtarma” |
| 5. | Concrete products, thous. m3 | 26,6 | 16,0 | 5,7 | 34 | Production base of Evrascon/MO-1 |
| 6. | Re-bar and embedded parts, ton | 3 767 | 3 157 | 1150,2 | 36 | “Mechel” |

- Personnel mobilization:

| № | Description | Requirement for 2015 | As of date |  |
| --- | --- | --- | --- | --- |
|  |  |  |  | foreign | local |
| 1 | Engineers | 65 | 62 | 21 | 41 |
| 2 | Lab. | 10 | 7 | 2 | 5 |
| 3 | Survey | 10 | 7 | 3 | 4 |
| 4 | Operators | 60 | 50 | 10 | 40 |
| 5 | Dump trucks drivers | 70 | 66 | 1 | 65 |
| 6 | Labors | 200 | 92 | 25 | 67 |
| 7 | Assembler, mounters | 70 | 34 | 4 | 30 |
| 8 | Others | 100 | 39 | 4 | 35 |
| Total | 585 | 357 | 70 | 287 |

- Equipment mobilization:

| № | Description | Requirement for 2015 | As of date | JV “Evrascon&MO-1” |
| --- | --- | --- | --- | --- |
|  |  |  |  | Evrascon | МО-1 |
| 1 | Dozer | 5 | 3 | 1 | 2 |
| 2 | Excavator | 5 | 3 | 2 | 1 |
| 3 | Loader | 5 | 2 | 1 | 1 |
| 4 | Grader | 3 | 1 | 1 | 0 |
| 5 | Roller | 5 | 3 | 2 | 1 |
| 6 | Dump trucks | 15 | 12 | 8 | 4 |
| 7 | Water tank | 3 | 2 | 2 | 0 |
| 8 | Asphalt paver | 2 | 0 | 0 | 0 |
| 9 | Crane | 10 | 8 | 4 | 4 |
| 10 | Cement concrete plant | 3 | 3 | 1 | 2 |
| 11 | Pile driver | 5 | 3 | 3 | 0 |
| 12 | Trail | 5 | 2 | 1 | 1 |
| 13 | Mixer | 10 | 5 | 2 | 3 |
| 14 | Vehicles | 25 | 19 | 10 | 9 |
| 15 | Other | 10 | 10 | 10 | 0 |
| Total | 111 | 76 | 48 | 29 |

- List of Contractor’s IPC

| IPC № | Date of report submission | Approval date | Amount (tg) | Remark |
| --- | --- | --- | --- | --- |
| 1 | 05.12.2013 | 06.12.2013 | (15%) Advance payment 1 020 456 288,61 tg | Advance payment |
| 2 | 11.05.2014 | 24.05.2014 | 172 663 285,52 | IPC №2 |
| 3 | 01.07.2014 | 05.07.2014 | 240 331 575,20 | IPC №3 |
| 4 | 20.09.2014 | 26.09.2014 | 170 284 187,84 | IPC №4 |
| 5 | 21.09.2014 | 10.10.2014 | 144 818 024,37 | IPC №5 |
| 6 | 10.09.2014 | 11.11.2014 | 141 735 431,65 | IPC №6 |
| 7 | 04.12.2014 | 12.11.2014 | 330 868 586,02 | IPC №7 |
| 8 | 06.02.2015 | 12.02.2015 | 128 787 398,13 | IPC №8 |
| 9 | 06.03.2015 | 15.03.2015 | 137 381 614,57 | IPC №9 |
| 10 | 10.04.2015 | 16.04.2015 | 119 528 927,76 | IPC №10 |
| 11 | 15.05.2015 | 02.06.2015 | 151 669 905,81 | IPC №11 |

- Variation Order

| № of VO | Description | Date of approval | Amount (tg) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | Relocation and reinstallation of safety fence in border area | 28.04.2014 | 19 210 685,34 | Returned for recalculation of currency. |
| 2 | Soil replacement due to insufficient bearing capacity of foundation | 06.11.2014 | 2 800 293,70 | Approved by Employer |
| 3 | Redesign of bridges Pk 852+45, Pk 888+10 and protection works at Pk 873+96 | 11.11.2014 | 24 473 994,72 | Returned for recalculation of currency. |
| 4 | Design change of bridges at Khorgos according to requirements of NSC of RK | 15.03.2015 | 29 073 012,99 | Returned for recalculation of currency and estimation of new price |

- Contractor’s Claims (Notice of claims)

| № | Submission date | Title | Remarks |
| --- | --- | --- | --- |
| 1 | 19.09.2014 | Works in frontier zone | Notice of claim No. 7/1 |
| 2 | 28.08.2014 | Diesel fuel lack | Notice of claim No. 7/2 |
| 3 | 19.09.2014 | Filling behind abutment | Notice of claim No. 7/3 |
| 4 | 19.09.2014 | Pile foundation transition | Notice of claim No. 7/4 |
| 5 | 01.10.2014 | Access roads | Notice of claim No. 7/5 |
| 6 | 13.01.2015 | The lack of modified traffic way levels | Notice of claim No. 7/6 |
| 7 | 17.01.2015 | Down time on construction sites. | Notice of claim No. 7/7 |
| 8 | 30.03.2015 | The lack of design drawings at Pk 272+18, Pk 334+67, Pk 233+20. | Notice of claim No. 7/8 |
| 9 | 30.03.2015 | The lack of design drawings on consolidation of Khorgos river bed | Notice of claim No. 7/9 |
| 10 | 31.03.2015 | Prolongation due to unsolved problems on Pk 873+96, Pk 888+10. | Notice of claim No. 7/10 |
| 11 | 19.05.2015 | Geology non-conformity to tender data at Pk 655+33, Pk 660+44, Pk 663+37, Pk 704+99, Pk 738+22, Pk 752+00. | Notice of claim No. 7/11 |