INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Oblast

as on 05.04.2016

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount:2 192 555 013.59 tenge

Commencement date: 08.04.2015

Completion period – 18 months (540 days)

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts (nos), incl.: | 82 |
| cattle pass | 6 |
| Transport interchange in two levels(nos) | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 651.52 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

Laboratory of the Contractor is equipped for 100%.

Testing in the meteorology and standardization of SKO is done. The certification is received. The Laboratory room confirms to requirement of Specifications.

3. Office of the Engineer and General Contractor

The office of the Engineer is at km.754 LHS in the village Sharaphana. The Contractor provided office to the Engineer with all necessary office equipment, office furniture and household appliances according to the specification. The territory is fenced and access road is repaired, there is a shed for parking, alternative sources of industrial water and electricity are installed.

The office of the General Contractor is on production camp, at km.760 RHS. The office is equipped with all necessary office equipment, office furniture and household appliances. Also meeting room for 30 people, dormitory for 100 people and two dining rooms (for local and foreign staff) are available there. All utilities (electricity, water, internet) are connected, there are alternative sources of industrial water and electricity.

4. Camp

The Camp of the General Contractor is completed for 100%. The whole territory is fenced, there are areas for storage of road construction materials, elements and constructions, silos for storage of the cement (2 nos with 500tns capacity each and 3nos with 200tns capacity each); the areas for parking and repairing of the road construction machinery; two cement-concrete plants (180m3 each); one plant for production of CSSCM (production capacity 180m3/per hour); silos for cement (for base 500m3); reservoirs for drinking water (180m3), reservoirs for technical water (3nos with 150m3 capacity each), reservoirs for fuel storage (200m3) and weight bridge;.

5. Surveying works:

The works for acceptance and repair of benchmarks, the arrangement of road axes on the length of the road are completed.

The works on measurement of graded elevation of the sections after milling of the existing pavement, measurement of graded elevations of subgrade, base course, cement concrete pavement, and checking of the levels of base and foundations of the culverts, underpasses and minor bridges for agricultural machinery are being carried out.

6. Works on artificial structures:

As on date 25 artificial structures are under construction. On 17 of them the erecting of reinforced concrete structures are completed, on 3 of them the monolithic foundation is arranged. 12 of them are being backfilled.

Also pile driving works on the bridge across the river Sharbulak is being carried out (80%), monolithic grillage of the third pillar is laid (20%). The overpass is being dismantled (50%), pile driving (20%), monolithic grillage (20%) and the bridge acrocc BKMK channel is dismantled for 50%.

To date, work there is carry being out construction of artificial construction on 6 sites. Completed works on the installation reinforced concrete construction on 75 sites. Balance work on the main road is 10 culverts and 29 pipes  at ramps.

Bridge and overpass works.

PК 610 bridge over the river Keles – erection  Т- beams– 35% (LHS);

PК 621 Bridge over the river Sharbulak – open moving traffic  for transport stream driveway

PК 636 overpass at Turbat –– erection  Т- beams 64%.

PК 663 bridge over the river BKMK – device protective layer on the right side, left side open for traffic flow.

Works on the overpass for agricultural machinery pass

PК 446+54; PК 505+53; PК 543+43;PК 583+60 – works on construction of overpass for agricultural equipment is completed. Balance of work –pavement of overpass, installation of  guard rails.

7. Communications relocation:

- Gas pipeline: the relocation of gas pipeline at PK 621 (bridge across Sharbulak river), PK 610 (bridge across Keles river)   and PK 636 (overpass at Turbat) are completed

- Communication lines: relocation of “Kazakhtelecom” communication line at PK 663 (bridge across BKMK channel) and PK 490 village Sharapkhana  is finished, relocation of “TUSM-11” communication line at PK 610 (bridge across Keles river) and PK 621 (bridge across Sharbulak river))are being carried out.

8. Procurement of the main road-building materials

| No | Materials | Unit | Plan on Contract | Actual for 2015 | Plan for 2016 | Actual for 2016 | Cumulative fact | % executing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone | Thous.m3 | 409,00 | 214,02 | 194,98 | 0,00 | 214,02 | 52,3% |
| 2 | GSM | Thous.m3 | 453,00 | 158,07 | 294,93 | 98,75 | 256,82 | 56,7% |
| 3 | Sand | Thous.m3 | 75,60 | 27,29 | 48,31 | 12,55 | 39,84 | 52,7% |
| 4 | Cement | Thous.m3 | 142,20 | 24,32 | 117,88 | 2,42 | 26,74 | 18,8% |
| 5 | Precast goods | Thous.m3 | 7,40 | 4,73 | 2,67 | 1,51 | 6,24 | 84,3% |

9. Progress of works:

| No | Description | Unit | Plan under contract | Actual for 2015 | Plan for 2016 | Actual 2016 | Cumulative fact | % executing |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks | М3 | 736,16 | 242,66 | 493,50 | 26,76 | 269,42 | 36,6% |
|  |  | km | 65,21 | 24,00 | 41,21 | 0,30 | 24,30 | 37,3% |
| 2 | Subbase | km | 65,21 | 19,74 | 45,47 | 2,38 | 22,12 | 33,9% |
| 3 | Base course | km | 65,21 | 19,39 | 45,82 | 1,99 | 21,38 | 32,8% |
| 4 | Concrete pavement | km | 62,43 | 16,98 | 45,45 | 1,43 | 18,41 | 29,5% |
| 5 | Culverts on the main road | pc | 46,00 | 24,21 | 21,79 | 9,66 | 33,87 | 73,6% |
| 6 | Pipes on the ramps | pc | 30,00 | 0,00 | 30,00 | 0,00 | 0,00 | 0,0% |
| 7 | Cattle pass | pc | 7,00 | 4,60 | 2,40 | 0,53 | 5,13 | 73,3% |
| 8 | Bridges | pc | 3,00 | 1,40 | 1,60 | 0,68 | 2,08 | 69,3% |
| 9 | Overpass | pc | 1,00 | 0,36 | 0,64 | 0,29 | 0,65 | 65,0% |
| 10 | Agr. Machinery pass | pc | 4,00 | 3,58 | 0,42 | 0,09 | 3,67 | 91,8% |
| 11 | Milling | km | 62,43 | 31,50 | 30,93 | 5,90 | 37,40 | 59,9% |
| 12 | Lean concrete removal | km | 62,43 | 24,74 | 37,69 | 0,44 | 25,18 | 40,3% |

10. Personnel:

| № | Name | Plan | Actualт | Из них |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign China | Local RK |
| 1 | Administration | 10 | 4 | 2 | 2 |
| 2 | ETD | 8 | 7 | 4 | 3 |
| 3 | Surveyor | 6 | 4 | 3 | 1 |
| 4 | Surveyor’s assistant | 7 | 3 |  | 3 |
| 5 | Laboratory Engineer | 1 | 1 | 1 |  |
| 6 | Laboratory assistant | 2 |  |  |  |
| 7 | Lab worker | 4 | 2 |  | 2 |
| 8 | Mechanic Engineer | 2 | 1 | 1 | 0 |
| 9 | Mechanic | 96 | 12 |  | 12 |
| 10 | Dumper’s driver | 129 | 16 |  | 16 |
| 11 | Mechanic’s assistant | 12 | 13 | 1 | 12 |
| 12 | Road Workers | 20 | 10 |  | 10 |
| 13 | Supporting staff | 54 | 64 |  | 64 |
| 14 | Office manager | 1 | 1 | 1 | 0 |
| 15 | Office staff | 21 | 10 | 6 | 4 |
| TOTAL | 373 | 148 | 19 | 129 |

Note:

Local personnel (129 people):

95 pers. – Kazygurt region;

6 pers. – Saryagash region;

2 pers. – Tolebi region;

3 pers. – Makhtyaral region;

2 pers. – Sayram region;

1 pers. – Sozak region;

6 pers. – Baidibek region;

2 pers. – Tulkubass region;

12 pers. – Shymkent city;

.

11. Equipment:

| № | Name | Plan for (December) | The fact the current date | mobilization |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | subcontr/rented |
| 1 | Bulldozer | 4 | 1 | 1 | 0 |
| 2 | Excavator | 10 | 6 | 3 | 3 |
| 3 | Loader | 11 | 6 | 4 | 2 |
| 4 | Dump | 100 | 31 | 25 | 6 |
| 5 | Water tanker | 7 | 3 | 2 | 1 |
| 6 | Fuel tanker | 1 | 3 | 1 | 2 |
| 7 | Grader | 8 | 5 | 3 | 2 |
| 8 | Roller | 18 | 5 | 3 | 2 |
| 9 | CCP 180m3/h | 2 | 2 | 2 |  |
| 10 | Installation for the base | 1 | 1 | 1 |  |
| 11 | Concrete paver | 1 | 2 | 2 |  |
| 12 | Base paving machine | 2 | 2 | 2 |  |
| 13 | Crane | 3 | 2 | 1 | 1 |
| 14 | Trailer | 2 |  |  |  |
| 15 | Vehicle | 15 | 14 | 10 | 4 |
| 16 | Milling machine | 1 | 1 | 1 |  |
| 17 | Other | 59 | 28 | 28 |  |
| TOTAL | 245 | 113 | 89 | 24 |

12. IPC

| № IPC |  | Plan | Actual | % development |
| --- | --- | --- | --- | --- |
| 1 | November 2014 | 100 039 703,68 | 100 039 703,68 | 100 % |
| 2 | April 2015 | 227 460 000,00 | 534 725 686,10 | 235 % |
| 3 | May 2015 | 529 770 000,00 | 736 304 069,65 | 47% |
|  | June 2015 | 1 024 670 000,00 |  |  |
| 4 | July 2015 | 1 128 920 000,00 | 704 648 065,67 | 62% |
| 5 | August 2015 | 1 142 300 000,00 | 709 548 604,88 | 62% |
| 6 | September 2015 | 586 920 000,00 | 395 935 912,96 | 67% |
| 7 | October 2015 | 495 100 000,00 | 319 353 665,73 | 65% |
| 8 | November2015 | 321 030 000,00 | 319 326 946,16 | 44% |
|  | December 2015 | 397 730 000,00 |  |  |
| 9 | January 2016 | - | 294 053 400,68 | - |
| 10 | February 2016 | 226 200 000,00 | 149 347 056,76 | 66% |
| Total |  | 8 285 111 815,26 | 4 263 072 674,89 | 62% |

13.  Variation order

| № | Period | Amount | Note |
| --- | --- | --- | --- |
| 1 | Replacement of geotextile for reinforced plastic film | - 46 209 603.85 | Approved CFR 23-23-03/2996 dated18.11.15 |
| 2 | Lean concrete. Dismantling of existing lean concrete layer | + 212 300 292.69 | Approved CFR 23-23-03/2996 dated 18.11.15 |
| 3 | Construction of RMD | Not determined | In progress |
| 4 | Relocation of communication line | Not determined | In progress |

14. Subcontractor organization:

| № | Name of Sub.organization | Type of work | Note |
| --- | --- | --- | --- |
|  | "Baku Stroi" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/1797 dated 22.07.2015 |
|  | "ART-Kurylys" LLP | Erecting of artificial structures (culverts, tubing and cattle passes) | Approved by COR ref.№ 23-23-03/1796 dated 22.07.2015 |
|  | “Bereke А” Corporation" | Construction of bridges and underpasses | Approved by COR ref.№ 23-23-03/1799 dated 22.07.2015 |
|  | "Mega-Tech" LLP | Relocation of telephone line (Kazakhtelecom) | Approved by COR ref.№ 23-23-03/976 dated 30.04.2015 |
|  | "BerkutMika" LLP | Earthworks and sub base | Approved by COR ref.№ 23-23-03/2498 от 02.10.2015 |
|  | "Kazspetselectromontazh PGS" LLP | Relocation of PTL | Approved by COR ref.№ .№ 23-23-03/2498 от 02.10.2015 |

15. Supplier of materials:

| № | Material | Supplier | Note |
| --- | --- | --- | --- |
| 1 | Crushed stone | Birlik 4 | For base |
|  |  | IP Tulemetov | For base |
| 2 | GSM | Kurbek I Kom |  |
| 3 | Sand | Kurbek I Kom |  |
| 4 | Cement | Standart cement | For pavement |
|  |  | Shymkent Cement | For pavement |
| 5 | Film (geomembrane) | Kyrylys Polimet |  |
|  |  | Kaz Geo Bel-1 |  |
| 6 | Dowel bar | Villar Kazakhstan |  |
|  |  | Kor Metal servic |  |
| 7 | Anchor | Mechel Kazakhstan |  |
| 8 | RSE for bridge | Bereke A |  |
| 9 | RSE for pipes and tubes | ART Kurulys |  |

16. Problem issues:

* According to the results of monitoring of progress, the Contractor has a growing delay from the Work Program. Considering the limited period of construction, Contractor needs to take radical measures for the recovering the delay in order to avoid the penalties by the Employer in accordance with GCC 8.7 [Delay damages].

* Contractor has a shortage of qualified personnel with experience in the road construction, from the management personnel competent for the planning and organization of work to the workers on the site Contractor needs to solve the problem of the personnel as per Clause 6.9 of GCC

* Transfer of pipeline along the  agricultural machinery pass, near the village. Aschibulak at PK 608 + 55.

* Bridge works are carrying out are very slow because of the lack of proper control by the Contractor.

* Construction of  Road Maintenance Depo(RMD) on the pass Kazygurt. Construction and erection work stopped, because there is  issue  regarding transfer of construction site.

Resident Engineer  						          Irmanov S.

Prep.by. Quantity Engineer

Mamanazarov B.