INFORMATION

Reconstruction of International Transit Corridor

“Western Europe – Western China”

km742-774 (LOT 1) in South Kazakhstan Region

as on 13.03.2017.

Contract: EBRD/CW-01/2013

Employer: Committee for Roads Ministry of Investments and Development RK

General Contractor : «SinohydoCorporationLimited»  (China)

SCS: «KazDorNII» in association with «KAzNIIPI» Dortrans KHA

Designer – “SK Engineering” LLP

Cost of the Contract: 14 617 033423.74 tenge

Advance payment amount: 2 192 555 013.59 tenge

Commencement date: 08.04.2015

Completion period – 15.12.2016 taking into account extension  16.11.2016 issued Certificate about Completion of part of the  work according to the GCC 10.2

1. Basic indicators

| Length of the section (km) | 32 |
| --- | --- |
| Culverts on the main road, (nos) | 46 |
| cattle pass (nos) | 7 |
| Culverts at ramps (adjunction) (nos) | 34 |
| Traffic interchange in two levels,nos | 1 |
| Bridges, underpasses, agricultural machinery pass (nos) | 3 /1 /4 |
| Earthworks (ths. m3) | 651.52 |
| GSM С-4 for sub base thick. Н=35cm(ths. m3) | 483.54 |
| CSGSM С-6 reinfor. 7% cement for base coarse thick. Н=20cm(ths. m3) | 227.71 |
| Cement concrete pavement Btb-4,8 – strength in bending; B-35 strength in compression thick. Н=27cm(ths. m3) | 208.67 |
| Bus pavilions / Bus stops | 10 / 10 |
| Rest area with ramp for vehicles in case of emergency situations, nos/Two-points Toillets nos | 4 / 4 |

2. Laboratory:

Laboratory of the Contractor is equipped for 100%.

Testing in the meteorology and standardization of SKO is done. The certification is received. The Laboratory room confirms to requirement of Specifications.

3. Office of the Engineer and General Contractor

The office of the Engineer is at km.754 LHS in the village Sharaphana. The Contractor provided office to the Engineer with all necessary office equipment, office furniture and household appliances according to the specification. The territory is fenced and access road is repaired, there is a shed for parking, alternative sources of industrial water and electricity are installed.

The office of the General Contractor is on production camp, at km.760 RHS. The office is equipped with all necessary office equipment, office furniture and household appliances. Also meeting room for 30 people, dormitory for 100 people and two dining rooms (for local and foreign staff) are available there. All utilities (electricity, water, internet) are connected, there are alternative sources of industrial water and electricity.

4. Camp

The Camp of the General Contractor is completed for 100%. The whole territory is fenced, there are areas for storage of road construction materials, elements and constructions, silos for storage of the cement (2 nos with 500tns capacity each and 3nos with 200tns capacity each); the areas for parking and repairing of the road construction machinery; two cement-concrete plants (180m3 each); one plant for production of CSSCM (production capacity 180m3/per hour); silos for cement (for base 500m3); reservoirs for drinking water (180m3), reservoirs for technical water (3 nos with 150 m3 capacity each), reservoirs for fuel storage (200m3) and weight bridge;.

5. Surveying works:

The works for acceptance and repair of benchmarks, the arrangement of road axes on the length of the road are completed. Also works on measuring the elevation of subgrade, CSSCM base course, cement concrete pavement, and checking of the levels of base and foundations of culverts, overpasses and small bridges for the of agricultural machinery passage.

6. Works on artificial structures:

Balance works on the main road - three culverts (ø1.5m) requiring repair, and construction of 22 culverts at the ramps (0,5 x 0,5m).

Works on bridges and overpasses.

PK 610 bridge over the river Keles –open the way for traffic flow on RHS ;

PK 621 bridge over the river Sharbulak - opened  traffic for  transport stream;

PK 636 overpass at Turbat - work on the overpass completed, work is underway at the ramps.

PK 663  bridge over BKMK channel - opened  traffic for  transport stream;

Works on the overpass for the agricultural machinery passage.

PK 446 + 54; PK 505 + 53; PK 543 + 43; PK 583 + 60 –open the way for traffic flow on the both sides . Balance of work-installation of guard rails, strengthen of slopes

7. Communications relocation:

• Transmission Line (ETL 0.4 kW and 10 kW.). All work on the reconstruction of power lines are completed;

• Pipeline. Work on the reconstruction of the line of the gas pipeline are completed, except for the section near the overpass Kazygurt - Turbat at PK 636. Work is underway on the device of housing. We note that the work on the reconstruction of the line of the pipeline have not been accounted for in the original contract.

• Lines of communication. (TUSM-11 and "Kazakhtelecom") All work on the communication line reconstruction completed. We note that according to the updated technical conditions, the actual amount of work on the reconstruction of more than was included in the original contract.

8. Procurement of the main road-building materials

| No | Materials | Unit | Plan on Contract | Actual for 2015-2016 | Plan for 2017 | Actual for 2017 | General fact | % executing | Rest |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Crushed stone | thous.m3 | 409,00 | 409,00 | - | - | 409,00 | 100,0% | - |
| 2 | GSM | thous.m3 | 453,00 | 450,18 | 2,82 | 1,12 | 451,30 | 99,6% | 1,70 |
| 3 | Sand | thous.m3 | 75,60 | 75,60 | - | - | 75,60 | 100,0% | - |
| 4 | Cement | thous.m3 | 104,17 | 104,17 | - | - | 104,17 | 100,0% | - |
| 5 | Precast goods | thous.m3 | 7,40 | 7,40 | - | - | 7,40 | 100,0% | - |

9. Progress of works:

| № | Description | Unit . | Plan on contract | Actual for 2015-2016 | Plan for 2017 | Actual for 2017 | General fact | % executing | Balance |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Subgrade | КМ | 64,74 | 64,74 | - | - | 64,74 | 100,0% | - |
| 2 | Subbase | КМ | 64,74 | 64,74 | - | - | 64,74 | 100,0% | - |
| 3 | Base course | КМ | 64,09 | 64,09 | - | - | 64,09 | 100,0% | - |
| 4 | Concrete pavement | КМ | 64,09 | 63,94 | 0,15 | - | 63,94 | 99,8% | 0,15 |
| 5 | Culverts on the main road | Nos | 46,00 | 46,00 | - | - | 46,00 | 100,0% | - |
| 6 | Culverts on the ramps | Nos | 30,00 | 3,00 | 26,00 | 5,00 | 8,00 | 26,6% | 22,00 |
| 7 | Cattle pass | Nos | 7,00 | 7,00 | - | - | 7,00 | 100,0% | - |
| 8 | Bridges | Nos | 3,00 | 2,85 | 0,15 | 0,05 | 2,95 | 98,3% | 0,05 |
| 9 | Overpass | Nos | 1,00 | 0,90 | 0,10 | - | 0,95 | 95,0% | 0,05 |
| 10 | Agr. Machinery pass | Nos | 4,00 | 3,95 | 0,05 | - | 3,95 | 98,8% | 0,05 |
| 11 | Milling | КМ | 64,09 | 64,09 | - | - | 64,09 | 100,0% | - |
| 12 | Lean concrete | КМ | 64,09 | 64,09 | - | - | 64,09 | 100,0% | - |
| 13 | Shoulders | КМ | 83,40 | 14,50 | 68,90 | 50,97 | 65,47 | 78,5% | 17,93 |
| 14 | Median strip | КМ | 21,70 | 3,30 | 18,40 | 18,40 | 21,70 | 100% | - |
| 15 | Trays | l.m | 9 728,00 | 2 826,00 | 6 902,00 | 3 194,00 | 7 356,00 | 75,6% | 2372,00 |
| 16 | Guard railings | КМ | 53,19 | - | 53,19 | 19,66 | 19,66 | 36,9% | 33,5 |
| 17 | Lightning poles | Nos | 512,0 | - | 512,0 | 188,0 | 342,0 | 66,7% | 170,0 |
| 18 | Road signs | Nos | 864,0 | - | 864,0 | 664,0 | 664,0 | 76,8% | 200,0 |
| 19 | Warning sign | Nos | 2 673,00 | - | 2 673,00 | - | - | - | 2673,00 |
| 20 | Road marking | КМ | 240,19 | - | 240,19 | - | - | - | 240,19 |
| 21 | Rest area | Nos | 4,0 | - | 4,0 | 0,5 | 0,5 | 12,5% | 3,5 |
| 22 | Bus-stop | Nos | 10,0 | - | 10,0 | - | - | - | 10,0 |

10. Personnel:

| No | Name | Plan | Actual | From them |
| --- | --- | --- | --- | --- |
|  |  |  |  | Foreign China | Local RK |
| 1 | Administration | 10 | 4 | 2 | 2 |
| 2 | ETD | 8 | 7 | 4 | 3 |
| 3 | Surveyor | 6 | 4 | 3 | 1 |
| 4 | Surveyor’s assistant | 7 | 3 |  | 3 |
| 5 | Laboratory Engineer | 1 | 1 | 1 |  |
| 6 | Laboratory assistant | 2 |  |  |  |
| 7 | Lab worker | 4 | 2 |  | 2 |
| 8 | Mechanic Engineer | 2 | 1 | 1 |  |
| 9 | Mechanic | 46 | 12 |  | 12 |
| 10 | Dumper’s driver | 29 | 16 |  | 16 |
| 11 | Mechanic’s assistant | 12 | 13 | 1 | 12 |
| 12 | Road Workers | 20 | 10 |  | 10 |
| 13 | Supporting staff | 54 | 64 |  | 64 |
| 14 | Office manager | 1 | 1 | 1 |  |
| 15 | Office staff | 21 | 10 | 6 | 4 |
| TOTAL | 223 | 148 | 19 | 129 |

Note:

Local personnel (129 people):

95 pers. – Kazygurt region;

6 pers. – Saryagash region;

2 pers. – Tolebi region;

3 pers. – Makhtyaral region;

2 pers. – Sayram region;

1 pers. – Sozak region;

6 pers. – Baidibek region;

2 pers. – Tulkubass region;

12 pers. – Shymkent city;

11. Equipment:

| № | Name | Plan for month | The fact the current date | From them: |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | subcontr/rented |
| 1 | Bulldozer | 4 | 1 | 1 |  |
| 2 | Excavator | 10 | 6 | 3 | 3 |
| 3 | Loader | 11 | 6 | 4 | 2 |
| 4 | Dump | 100 | 31 | 25 | 6 |
| 5 | Water tanker | 7 | 3 | 2 | 1 |
| 6 | Fuel tanker | 1 | 3 | 1 | 2 |
| 7 | Grader | 8 | 5 | 3 | 2 |
| 8 | Roller | 18 | 5 | 3 | 2 |
| 9 | CCP 180m3/h | 2 | 2 | 2 |  |
| 10 | Installation for the base | 1 | 1 | 1 |  |
| 11 | Concrete paver | 1 | 1 | 1 |  |
| 12 | Base paving machine | 2 | 2 | 2 |  |
| 13 | Crane | 3 | 2 | 1 | 1 |
| 14 | Trailer | 2 |  |  |  |
| 15 | Vehicle | 15 | 14 | 10 | 4 |
| 16 | Milling machine | 1 | 1 | 1 |  |
| 17 | Other | 59 | 28 | 28 |  |
| TOTAL | 245 | 112 | 88 | 24 |

12. Subcontractor company:

| No | Name of Subcontractor company | Type of works | Note |
| --- | --- | --- | --- |
| 1 | "Baku Stroi" LLP | Earthworks and sub base | Approved by CFR out.№ 23-23-03/1797 dated 22.07.2015 |
| 2 | "ART-Kurylys" LLP | installation of artificial structures (culverts) | Approved by CFR out.№ 23-23-03/1796 dated 22.07.2015 |
| 3 | “Bereke А” Corporation" | construction of bridges and overpasses | утвержден КАД out.№ 23-23-03/1799 dated 22.07.2015 |
| 4 | "Mega-Tech" LLP | reorganization/transfer of communication line (Kazakhtelekom) | Approved by CFR out.№ 23-23-03/976 dated 30.04.2015 |
| 6 | "Kazspetselectromontazh PGS" LLP | reorganization/transfer of the power line | Approved by CFR out.№ 23-23-03/2498 dated 02.10.2015 |
| 7 | “Mego energo” LLP | Construction of RMD | Approved by CFR out.№ 23-23-03/4729 dated 15.02.2016 |

13. Supplier of materials:

| No | Material | Supplier | Note |
| --- | --- | --- | --- |
| 1 | Crushed stone | Birlik 4 | For pavement |
|  |  | IP Tulametov | For base |
| 2 | GSM | Kurbek I Kom, Aigana |  |
| 3 | Sand | Kurbek I Kom |  |
| 4 | Cement | Standart cement | For pavement |
|  |  | Shymkent Cement | For base |
| 5 | Film (geomembrane) | Kyrylys Polimet |  |
|  |  | Kaz Geo Bel-1 |  |
| 6 | Dowel bar | Villar Kazakhstan |  |
|  |  | Kor Metal service |  |
| 7 | Anchor bar | Mechel Kazakhstan |  |
| 8 | Precast goods for bridges | Bereke A |  |
| 9 | Precast goods culverts and tubing | ART Kurulys |  |