INFORMATION

Implementation of Western Europe –Western China Project

Almaty-Khorgos Roads, section km 111.7 – 171.1

Almaty Oblast, Lot 3

As of 20.01.2017

Contract : EWRP- 111,7- 171,1- ICB(W)-001/2013

Designer :  Kazdorproject LLP

Consultant:  Dongsung Engineering/Dongmeoung/ Zhol-Sapa LLP

General Contractor: Todini/Impregilo/Kazakhdorstroi JV

Subcontractors: AZMK Service LLP, Vesta Trans Service LLP, Zhanbota Trans Service LLP, Montazhnik LLP, Asia Energo Stroi LLP, Almaty Svyaz Stroi LLP, Temad LLP.

Laboratory:  Contractor’s property

Contractor’s Contract Amount: 14 683 716 863,20 KZT

Disbursed up to 2016: 9 455 705 786 KZT

Disbursement Plan 2016: 6 756 790 970 KZT

Construction time: 1137 calendar days

Construction time 2013 – 2016

Summary of Project:

Source of financing:  World Bank

Road Category:  I b

Length 59,5 km

Type of upper layer of pavement: concrete (25cm)

Thickness of road pavement (76cm)

Executive documents:

Number of instructions 0 nos, letters 12 nos issued per week

Dead line of submission of Work Production Project, and Quality Control Plan - 07.04.2016 actual

(reason of delay)

- Basic

| Description | Total Contract | Plan 2016 | Actual as of date |
| --- | --- | --- | --- |
| Bridge |  |  |  |
| Cattle pass | 8 | - | 8 |
| Overpass |  |  |  |
| Interchange | 1,00 | 0,22 | 1,00 |
| Culverts | 57 | - | 57 |
| Bus shelter |  |  |  |
| Road Maintenance Facility |  |  |  |
| Overhead road | 6 | 6 | - |

| № | Description of works | Total Contract | Performed in 2013-2015 | Plan for 2016 | Actual 2016 | % |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Earthworks (thous m3) | 3785,47 | 3785,47 | 727,01 | 3785,47 | 100 |
| 2 | Concrete pavement, km | 59,5 | 32,54 | 26,96 | 56,85 | 95,5 |
| 3 | Base course, km | 59,5 | 34,42 | 25,08 | 59,5 | 100 |
| 4 | Subbase, km | 59,5 | 51,75 | 7,75 | 59,5 | 100 |
| 5 | Asphalt pavement on median line, km | 59,5 | 0,00 | 59,5 | 36,39 | 61,2 |
| 6 | Installation of guardrails, r/m (median line) | 58446 | 0,00 | 58446 | 35335 | 60,4 |
| 7 | Installation of guardrails, r/m | 16434 | 0,00 | 16434 | 1808 | 11,0 |

- Material Stockpile 2016:

| № | Description | Total Contract | 2016 | Suppliers |
| --- | --- | --- | --- | --- |
|  |  |  | Plan | Actual as of date | % |  |
| 1. | Crushed stone, thous cum | 691,41 | 111,38 | 50,53 | 45,37 | Todini |
| 2. | Sand, thous cum | 51,78 | 38,35 | 8,02 | 20,91 | Todini |
| 3. | SGM, thous cum | 607,86 | 65,82 | 65,82 | 100 | Todini |
| 4 | Cement, thous ton | 146,07 | 108,2 | 8,57 | 7,92 | Semei Cement |
| 5 | PC elements, thous cum | 3,45 |  |  | 0,00 | AZMK |

- Mobilization of Equipment:

| № | Description | Requirement 2016 | Actual as of date | Out of them |
| --- | --- | --- | --- | --- |
|  |  |  |  | own | Sucontractors’/rented |
| 1 | Dozer | 9 | 5 | 4 | 1 |
| 2 | Excavator | 13 | 6 | 5 | 1 |
| 3 | Loader | 12 | 15 | 13 | 2 |
| 4 | Grader | 6 | 6 | 4 | 2 |
| 5 | Rollers | 15 | 11 | 9 | 2 |
| 6 | Dump truck | 50 | 51 | 46 | 5 |
| 7 | Water sprinkler | 15 | 23 | 21 | 2 |
| 8 | Petrol tanker | 2 | 2 | 2 |  |
| 9 | Asphalt paver | 4 | 4 | 4 |  |
| 10 | Concrete paver | 1 | 2 | 2 |  |
| 11 | Milling machine | 1 | 1 | 1 |  |
| 12 | Auto Crane | 6 | 4 | 2 | 2 |
| 13 | Power distributor |  |  |  |  |
| 14 | ACP | 1 | 1 | 1 |  |
| 15 | CCP | 3 | 3 | 3 |  |
| 16 | Crushing and screening plant | 2 | 2 | 2 |  |
| 17 | Piling machine |  |  |  |  |
| 18 | Low loader | 5 | 4 | 4 |  |
| 19 | Concrete mixer | 3 | 2 | 2 |  |
| 20 | Otehrs | 40 | 44 | 42 | 2 |
| Total | 188 | 186 | 167 | 19 |