As per 2.09.2015

INFORMATION

For implementation of section km 171.1 – km 214.3 “Almaty – Khorgos” Road

Western Europe – Western China Project in Almaty Region

Contractor «JV «Todini /Impregilo -Kazakhdorstroi», Lot 4

Main Contractor – СП «Todini /Impregilo-Казахдорстрой»

Contract – EWRP-171.1-214.3-ICB(W)-001/2013

Contract Amount - 12 423 346 359 KZT

Contract signed – 30.07.2013

Construction period – 22 / 10 / 2013 – 09 /.04 / 2016

Disbursed in 2014 – 2 286 617 464 KZT

Disbursement plan for 2015 – 3 483 800 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazdorproject”

- Main Project characteristics

| Length, km | 43.3 |
| --- | --- |
| Culverts, no’s. | 28 |
| Bridges and cattle creeps, nos. | 4 |
| Overpasses, nos. | 1 |
| Interchanges, no’s. | 0 |
| Earthworks, thous.m3 | 3 069 |
| Sub base, km/thous.m3 | 43.3 / 466 |
| CSCSM, km/thous.m3 | 43.3 / 179 |
| Cement concrete pavement, km/thous.m3 | 43.3 / 202 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Prior to variation | After variation |  |  | remain | % | remain | % |
| 1. | Earthworks (thous.m3) | 3 069 | 2 828,8 | 1 127,9 | 657.69 | 414.02 | 63% | 285.32 | 91% |
|  | Strengthening layer for embankment |  |  |  | 56,22 |  |  |  |  |
| 2. | Subbase, km | 43,2 | 38,3 | 21.19 | 17.11 | 55% | 16.81 | 61% |
| 3. | Base course from CSCSM, km | 43,2 | 29,9 | 11.71 | 18.19 | 39% | 31.59 | 27% |
| 4. | Cement concrete pavement, km | 43,2 | 29,7 | 0.00 | 29,70 | 0,0% | 43,3 | 0,0% |
| 5. | Bridges and overpasses, nos. | 5 | 3 | 5 in progress |  |  |  | 48% |
| 6. | Culverts, nos. | 28 | 20 | 21 completed 7 in progress | 3 | 85% | 11 | 61% |

- Procurement of materials for 2015:

| N | Description of material | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 290,86 | 168,68 | 96.98 | 57 |  |
| 2. | Sand, thous.m3 | 131,79 | 35,98 | 11,69 | 32 |  |
| 3. | SGM, thous.m3 | 544,82 | 459,87 | 168.78 | 37 |  |
| 4. | Cement, thous.m3 | 93,28 | 47,9 | 8.68 | 18 |  |
| 5. | RCP, thous.m3 | 6,20 | 6,20 | 3,85 | 62 |  |

- Personnel involvement:

| N | Description | Demand for 2015 | TOTAL actual | Main Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL | LLP "STA Profit Group" | LLP "Kerege Trans Service" | PC "Ruslan" | LLP "AZMK" |
| 1 | Engineers and Technicians, Administration | 17 | 74 | 29 | 9 | 20 | 45 | 9 | 11 | 10 | 15 |
| 2 | Laboratory Assistants and Quality Service | 8 | 12 | 12 | 2 | 10 | - | 0 | 0 | 0 | 0 |
| 3 | Operators of special machinery | 50 | 70 | 27 | 0 | 27 | 43 | 17 | 10 | 10 | 6 |
| 4 | Surveyors | 3 | 19 | 10 | 1 | 9 | 9 | 3 | 3 | 1 | 2 |
| 5 | Drivers of dumpers | 50 | 72 | 20 | 0 | 20 | 52 | 15 | 20 | 15 | 2 |
| 6 | Road workers | 20 | 111 | 17 | 0 | 17 | 94 | 5 | 4 | 4 | 81 |
| 7 | Welders |  | 13 | 2 | 0 | 2 | 11 | 0 | 1 | 0 | 10 |
| 8 | Others |  | 32 | 18 | 0 | 18 | 14 | 4 | 2 | 0 | 8 |
|  | TOTAL | 148 | 403 | 135 | 12 | 123 | 268 | 53 | 51 | 40 | 124 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2015 | TOTAL actual |
| --- | --- | --- | --- | --- |
| 1 | Bulldozer | pcs | 8 | 6 |
| 2 | Excavator | pcs | 7 | 12 |
| 3 | Loader | pcs | 6 | 23 |
| 4 | Motor grader | pcs | 4 | 6 |
| 5 | Rollers | pcs | 6 | 14 |
| 6 | Dumpers | pcs | 50 | 58 |
| 7 | Water tank | pcs | 4 | 14 |
| 8 | Petrol tank | pcs | 2 | 5 |
| 9 | Asphalt paver | pcs | 2 | 2 |
| 10 | Concrete paver | pcs | 1 | 0 |
| 11 | Milling machine | pcs | 1 | 1 |
| 12 | Truck crane | pcs | 4 | 5 |
| 13 | Distributor | pcs | 1 | 0 |
| 14 | ACP | pcs | 1 | 0 |
| 15 | CCP | pcs | 1 | 2 |
| 16 | Crusher | pcs | 1 | 1 |
| 17 | Cement warehouse | pcs | 1 | 0 |
| 18 | Sand washer | pcs | 1 | 0 |
| 19 | Crusher secondary | pcs | 1 | 0 |
| 20 | Batching plant | pcs | 1 | 6 |
| 21 | Mixer | pcs | 8 | 2 |
| 22 | Pile driver | pcs | 1 | 0 |
| 23 | Boring equipment for drilled piles | pcs | 2 | 1 |
| TOTAL | pcs | 114 | 158 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP "Afdan" | Filling embankment | CH 592+50 CH 721+00 | approved |
| 2 | LLP "STA Profit Group" | Filling embankment | CH 721+50 CH 870+00 | ongoing |
| 3 | LLP "Kerege Trans Service " | Filling embankment subbase |  | approved |
| 4 | LLP "AZMK" | Bridges, overpass | 4 bridges 1 overpass | approved |
| 5 | PC "Montazhnik" | Construction of culverts | 28 culverts | approved |

Problem issues:

| 1. | RMD – notification from GASK is not available. Cost increase for construction of RMD was not coordinated with Designer. |
| --- | --- |
| 2. | Problem was not solved for strengthening of roadside for sand dunes. |
| 3. | Problem was not solved with supply of cement for concrete pavement. |
| 4. | Slow progress of works for construction of culverts and bridges. |

Variations.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 4 | Increase for 707 140 120.44 KZT including VAT | Not approved | Corrected according to the Client’s comments. Ongoing. |