As per 16.06.2015

INFORMATION

For implementation of section km 171.1 – km 214.3 “Almaty – Khorgos” Road

Western Europe – Western China Project in Almaty Region

Contractor «JV «Todini /Impregilo -Kazakhdorstroi», Lot 4

Main Contractor – СП «Todini /Impregilo-Казахдорстрой»

Contract – EWRP-171,1-214,3-ICB(W)-001/2013

Contract Amount - 12 423 346 359 KZT

Contract signed – 30.07.2013

Construction period – 22 / 10 / 2013 – 09 /.04 / 2016

Disbursed in 2014 – 2 286 617 464 KZT

Disbursement plan for 2015 – 3 483 800 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazdorproject”

- Main Project characteristics

| Length, km | 43,3 |
| --- | --- |
| Culverts, no’s. | 28 |
| Bridges and cattle creeps, nos. | 4 |
| Overpasses, nos. | 1 |
| Interchanges, no’s. | 0 |
| Earthworks, thous.m3 | 3 069 |
| Sub base, km/thous.m3 | 43,3 / 466 |
| CSCSM, km/thous.m3 | 43,3 / 179 |
| Cement concrete pavement, km/thous.m3 | 43,3 / 202 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2015 | Actual for current date since 2015 start |
| --- | --- | --- | --- | --- |
| 1. | Earthworks (thous.m3) | 3 069 | 1 127,9 | 533.35 |
| 2. | Sub base, km | 43,3 | 38,3 | 20.05 |
| 3. | Base course from CSCSM, km | 43,3 | 29,9 | 5.21 |
| 4. | Cement concrete pavement, km | 43,3 | 29,7 | 0.00 |
| 5. | Bridges and overpasses, nos. | 5 | 3 | 5 in progress |
| 6. | Culverts, nos. | 28 | 20 | 13 completed 8 in progress |

- Procurement of materials for 2015:

| N | Description of material | Total under Contract | Plan for 2015 | Actual for current date since 2015 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 290,86 | 168,68 | 65.56 | 39 |  |
| 2. | Sand, thous.m3 | 131,79 | 35,98 | 5.74 | 16 |  |
| 3. | SGM, thous.m3 | 544,82 | 459,87 | 140.48 | 30 |  |
| 4. | Cement, thous.m3 | 93,28 | 47,9 | 3.62 | 7 |  |
| 5. | RCP, thous.m3 | 6,20 | 6,20 | 2,0 | 32 |  |

- Personnel involvement:

| No. | Description | Demand for 2015 | TOTAL actual | Main Contractor |  |  | Subcontractors |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | international | local | TOTAL |
| 1 | Engineers and Technicians, Administration | 17 | 63 | 25 | 9 | 16 | 38 |
| 2 | Laboratory Assistants and Quality Service | 8 | 11 | 11 | 2 | 9 | - |
| 3 | Operators of special machinery | 50 | 55 | 7 | 1 | 6 | 48 |
| 4 | Surveyors | 3 | 12 | 4 | 1 | 3 | 8 |
| 5 | Drivers of dumpers | 50 | 98 | 5 | - | 5 | 93 |
| 6 | Road workers | 20 | 72 | 5 | - | 5 | 67 |
| 7 | Welders |  | 7 | 1 | - | 1 | 6 |
| 8 | Others |  | 23 | 13 | - | 13 | 10 |
|  | TOTAL | 148 | 313 | 71 | 13 | 58 | 270 |

- Mobilization of equipment:

| No. | Description | Unit | Demand for 2015 | TOTAL actual | Main Contractor Todini | Total for Subcontractors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | own | rented |  |
| 1 | Bulldozer | nos. | 8 | 7 | 0 | 0 | 7 |
| 2 | Excavator | nos. | 7 | 12 | 5 | 0 | 7 |
| 3 | Loader | nos. | 6 | 13 | 5 | 0 | 8 |
| 4 | Motor grader | nos. | 4 | 8 | 0 | 0 | 8 |
| 5 | Rollers | nos. | 6 | 14 | 5 | 0 | 9 |
| 6 | Dumpers | nos. | 50 | 82 | 7 | 0 | 75 |
| 7 | Water tank | nos. | 4 | 11 | 4 | 0 | 7 |
| 8 | Petrol tank | nos. | 2 | 6 | 0 | 0 | 6 |
| 9 | Asphalt paver | nos. | 2 | 2 | 2 | 0 | 0 |
| 10 | Concrete paver | nos. | 1 | 0 | 0 | 0 | 0 |
| 11 | Milling machine | nos. | 1 | 0 | 0 | 0 | 0 |
| 12 | Truck crane | nos. | 4 | 3 | 1 | 0 | 2 |
| 13 | Distributor | nos. | 1 | 0 | 0 | 0 | 0 |
| 14 | ACP | nos. | 1 | 0 | 0 | 0 | 0 |
| 15 | CCP | nos. | 1 | 3 | 2 | 0 | 1 |
| 16 | Crusher | nos. | 1 | 2 | 0 | 2 | 0 |
| 17 | Cement warehouse | nos. | 1 | 1 | 0 | 0 | 1 |
| 18 | Sand washer | nos. | 1 | 0 | 0 | 0 | 0 |
| 19 | Crusher secondary | nos. | 1 | 0 | 0 | 0 | 0 |
| 20 | Batching plant | nos. | 1 | 1 | 0 | 0 | 1 |
| 21 | Mixer | nos. | 8 | 4 | 0 | 0 | 4 |
| 22 | Pile driver | nos. | 1 | 1 | 0 | 0 | 1 |
| 23 | Boring equipment for drilled piles | nos. | 2 | 1 | 0 | 0 | 1 |
| TOTAL | nos. | 114 | 158 | 31 | 2 | 138 |

- Subcontractors:

| No. | Name of Subcontractor | Type of work | Section from km to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP "Afdan" | Filling embankment | CH 592+50 CH 721+00 | approved |
| 2 | LLP "STA Profit Group" | Filling embankment | CH 721+50 CH 870+00 | ongoing |
| 3 | LLP " Stroy Expo KZ " | Filling embankment | CH 870+50 CH 1009+00 | approved |
| 4 | LLP "Kerege Trans Service " | Filling embankment subbase |  | approved |
| 5 | PC "Ruslan" | Filling embankment | CH 1009+00 CH1025+44 | approved |
| 6 | LLP "AZMK" | Bridges, overpass | 4 bridges 1 overpass | approved |
| 7 | PC "Montazhnik" | Construction of culverts | 28 culverts | approved |

Problem issues:

- Slow construction of culverts and bridges

- Slow procurement of materials

- Special machinery was not mobilized for construction of pavement (concrete paver)

- Supply of cement was not organized

- Variation Order No. 1 was not approved

- Problem was not solved regarding protection of roadside from wind erosion.

Variation Orders.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 4 | Increase for 707 140 120.44 KZT including VAT | Not approved | Corrected according to the Client’s comments. Ongoing. |