As per 30.03.2016

INFORMATION

For implementation of section km 171.1 – km 214.3 “Almaty – Khorgos” Road

Western Europe – Western China Project in Almaty Region

Contractor «JV «Todini /Impregilo -Kazakhdorstroy», Lot 4

General Contractor – JV «Todini /Impregilo-Kazakhdorstroy»

Contract – EWRP-171.1-214.3-ICB(W)-001/2013

Contract Amount - 12 423 346 359 KZT

Contract signed – 30.07.2013

Construction period – 18 / 10 / 2013 – 30 /11 / 2016

Disbursed in 2013-2015 – 6 480 211 047.47 KZT

Disbursement plan for 2016 – 5 943 135 311.53 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazdorproject”

- Main Project features

| Length, km | 43.3 |
| --- | --- |
| Culverts, no’s. | 28 |
| Bridges and cattlepasses, nos. | 4 |
| Overpasses, nos. | 1 |
| Interchanges, no’s. | 0 |
| Earthworks, thous.m3 | 3 069 |
| Sub base, km/thous.m3 | 43.3 / 466 |
| CSCSM, km/thous.m3 | 43.3 / 179 |
| Cement concrete pavement, km/thous.m3 | 43.3 / 202 |

- Analysis for work program performance:

| N | Description of works | Total under Contract | Plan for 2016 | Actual for current date from the beginning of 2016 | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Prior to variation | After variation |  |  | remain | % | remain | % |
| 1. | Earthworks (thous.m3) | 3 069 | 2 828,8 | 202,21 | - | 0 | 0% | 202,21 | 93% |
|  | Strengthening layer for embankment |  |  |  | - |  |  |  |  |
| 2. | Subbase, km | 43,3 | 8,75 | 5,85 | 2,9 | 67% | 2,9 | 94% |
| 3. | Base course from CSCSM, km | 43,3 | 23,56 | 2,9 | 20,66 | 13% | 22,64 | 52% |
| 4. | Cement concrete pavement, km | 43,3 | 38,35 | 0 | 38,35 | 0% | 38,35 | 10% |
| 5. | Bridges and overpasses, nos. | 5 | - | 5 in progress |  |  |  | 67% |
| 6. | Culverts, nos. | 28 | - | 28 completed | 0 | 0% | 0 | 100% |

- Procurement of materials for 2016:

| N | Description of material | Total under Contract | Plan for 2016 | Actual for current date since 2015 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 290,86 | 299,79 | 202,75 | 68 |  |
| 2. | Sand, thous.m3 | 131,79 | 43,11 | 12,71 | 30 |  |
| 3. | SGM, thous.m3 | 544,82 | 159,79 | 18,89 | 12 |  |
| 4. | Cement, thous.m3 | 93,28 | 78,22 | 1,64 | 2,1 |  |
| 5. | RCP, thous.m3 | 6,20 | 6,20 | 3,85 | 62 |  |

- Personnel involvement:

| N | Description | Demand for 2016 | TOTAL actual | General Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL | Sung Do | LLP "Kerege Trans Service" | LLP "AZMK" |
| 1 | Engineers and Technicians, Administration | 17 | 81 | 48 | 13 | 35 | 35 | 5 | 10 | 18 |
| 2 | Laboratory Assistants and Quality Service | 8 | 15 | 15 | 2 | 13 | - | 0 | 0 | 0 |
| 3 | Operators of special machinery | 50 | 66 | 22 | 0 | 22 | 44 | 3 | 14 | 27 |
| 4 | Surveyors | 3 | 23 | 15 | 0 | 15 | 8 | 0 | 6 | 2 |
| 5 | Drivers of dumpers | 50 | 45 | 23 | 0 | 23 | 22 | 0 | 20 | 2 |
| 6 | Road workers | 20 | 174 | 27 | 0 | 27 | 147 | 15 | 5 | 127 |
| 7 | Welders |  | 14 | 7 | 0 | 7 | 7 | 0 | 1 | 6 |
| 8 | Others |  | 34 | 26 | 0 | 26 | 8 | 2 | 2 | 4 |
|  | TOTAL | 148 | 452 | 183 | 15 | 168 | 269 | 25 | 58 | 186 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2016 | TOTAL actual |
| --- | --- | --- | --- | --- |
| 1 | Bulldozer | pcs | 8 | 3 |
| 2 | Excavator | pcs | 7 | 7 |
| 3 | Loader | pcs | 6 | 15 |
| 4 | Motor grader | pcs | 4 | 5 |
| 5 | Rollers | pcs | 6 | 12 |
| 6 | Dumpers | pcs | 50 | 53 |
| 7 | Water tank | pcs | 4 | 3 |
| 8 | Petrol tank | pcs | 2 | 2 |
| 9 | Asphalt paver | pcs | 2 | 2 |
| 10 | Concrete paver | pcs | 1 | 0 |
| 11 | Milling machine | pcs | 1 | 0 |
| 12 | Truck crane | pcs | 4 | 8 |
| 13 | Distributor | pcs | 1 | 0 |
| 14 | ACP | pcs | 1 | 0 |
| 15 | CCP | pcs | 1 | 2 |
| 16 | Crusher | pcs | 1 | 1 |
| 17 | Cement warehouse | pcs | 1 | 0 |
| 18 | Sand washer | pcs | 1 | 0 |
| 19 | Crusher secondary | pcs | 1 | 0 |
| 20 | Batching plant | pcs | 1 | 6 |
| 21 | Mixer | pcs | 8 | 2 |
| 22 | Pile driver | pcs | 1 | 0 |
| 23 | Boring equipment for drilled piles | pcs | 2 | 0 |
| TOTAL | pcs | 114 | 110 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 3 | LLP "Kerege Trans Service " | Filling embankment and subbase |  | approved |
| 4 | LLP "AZMK" | Bridges, overpass | 4 bridges 1 overpass | approved |
| 5 | Sung Do | Concrete pavement |  | approved |

Issues of concern:

| 1. | Cost increase for construction of RMD was not coordinated with Designer. |
| --- | --- |
| 2. | Problem was not solved for strengthening of roadside for sand dunes. |
| 3. | Problem was not solved with supply of cement for concrete pavement. |

Variations.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 4 | Increase for 707 140 120.44 KZT including VAT | Not approved | Corrected according to the Client’s comments. Ongoing. |