As per 20.01.2017

INFORMATION

For implementation of section km 214.3 – km 259.3 “Almaty-Khorgos” of Western Europe – Western China Road Project in Almaty Region Lot 5

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroy»

Contract – EWRP-214.3-259.3-ICB(W)-001/2013

Contract Amount - 15 973 021 205 KZT

Contract Amount – 16 343 628 501,00 KZT (considering variations No.1, No.2 and No.3)

Contract signed – 30.07.2013

Disbursed in 2013-2016 – 15 630 921 345,00 KZT

Disbursement plan for 2015 – 4 902 970 000 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazakhstan zholdary”

- Main Project characteristics

| Length, km | 45 |
| --- | --- |
| Culverts, no’s. | 48 |
| Bridges and cattle creeps, nos. | 0 |
| Overpasses, nos. | 0 |
| Interchanges, no’s. | 3 |
| Earthworks, thous.m3 | 6 728 |
| Sub base, km/thous.m3 | 45 / 443,04 |
| CSCSM, km/thous.m3 | 45 / 186,84 |
| Cement concrete pavement, km/thous.m3 | 45 / 208,17 |

- Analysis for work schedule performance:

| № | Description of works | Total under Contract | performed up to 2016 | Plan for 2016 | Actual performed Total | Performed in 2016 | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Remain. | % | remain. | % |
| 1 | Earthworks (thous.m3) | 4 382,27 | 3 033,48 | 793,9 | 3 819,03 | 785,55 | 0,00 | 100% | 0,00 | 100% |
|  | Strengthening layer for embankment |  | 554,89 |  | 563,24 | 8,35 |  |  |  |  |
| 2 | Subbase, km | 44,00 | 31,81 | 12,19 | 44,00 | 12,19 | 0,00 | 100% | 0,00 | 100% |
| 3 | Base course from CSCSM, km | 43,70 | 21,22 | 22,48 | 43,70 | 22,48 | 0,00 | 100% | 0,00 | 100% |
| 4 | Cement concrete pavement, km | 43,50 | 21,06 | 22,44 | 43,50 | 22,44 | 0,00 | 100% | 0,00 | 100% |
| 5 | Expansion joint | 367,21 |  | 127,68 | 204,06 | 204,06 |  |  | 163,15 | 55,57% |
| 6 | Strengthening of shoulders, km | 43,50 | 0,00 | 43,50 | 0,00 | 43,50 | 0,00 | 100% | 0,00 | 100% |
| 7 | Base of dividing strip, km | 43,10 | 0,00 | 43,10 | 43,10 | 43,10 | 0,00 | 100% | 0,00 | 100% |
| 8 | Asphalt, dividing strip, km | 43,10 | 0,00 | 43,10 | 43,10 | 43,10 | 0,00 | 100% | 0,00 | 100% |
| 9 | Guardrail (axe), rm | 88,11 | 0,00 | 88,11 | 53,40 | 69 | 19,51 | 78,31% | 19,51 | 78,31% |
| 10 | Guardrail (shoulder), rm. | 73,64 | 0,00 | 73,64 | 0,00 | 0,00 | 73,64 | 0,00% | 73,64 | 0,00% |
| 11 | Road marking, rm. | 43,10 | 0,00 | 43,10 | 0,00 | 0,00 | 43,10 | 0,00% | 43,10 | 0,00% |
| 12 | Chutes, rm | 20,45 | 0,00 | 20,45 | 2,80 | 13,9 | 6,55 | 67,98% | 6,55 | 67,98% |
| 13 | Culverts, pcs/ | 64,00 | 63 | 1 | 64,00 | 0,00 | 0,00 | 0,00% | 0,00 | 100% |
| 14 | Strengthening layer for embankment (culverts) |  | 17,44 |  | 17,44 |  |  |  |  |  |
| 15 | Geotextile, m2 |  | 961 |  | 960,60 |  |  |  |  |  |

- Procurement of materials for Заготовка материалов на 2015 год:

| N | Description of material | Total under Contract | Plan for 2016 | Actual for current date | Suppliers |
| --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 398,32 | 25,42 | 25,27 | “JV SineMidasStroi” |
| 2. | Sand, thous.m3 | 42,02 | 3,85 | 3,85 |  |
| 3. | SGM, thous.m3 | 538,14 | 220,13 | 216,52 | “JV SineMidasStroi” |
| 4. | Cement, thous.m3 | 112,41 | 57,48 | 52,858 |  |
| 5. | RCP, thous.m3 | 4.61 | 0,08 | 0,08 | LLP AZMK |

- Personnel involvement Привлечение персонала:

| N | Description | Demand for 2016 | TOTAL actual | Main Contractor | Subcontractors |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local | TOTAL |
| 1 | Engineers and Technicians, Administration | 37 | 28 | 16 | 14 | 0 | 12 |
| 2 | Laboratory Assistants and Quality Service | 8 | 8 | 4 | 1 | 3 | 4 |
| 3 | Operators of special machinery | 71 | 39 | 0 | 0 | 0 | 39 |
| 4 | Surveyors | 4 | 3 | 0 | 0 | 0 | 3 |
| 5 | Drivers of dumpers | 80 | 10 | 0 | 0 | 0 | 10 |
| 6 | Road workers | 40 | 46 | 0 | 0 | 0 | 46 |
| 7 | Welders |  |  |  | 0 |  |  |
| 8 | Others | - |  |  | 0 | - | - |
|  | TOTAL | 240 | 137 | 20 | 15 | 3 | 114 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2016 | TOTAL actual | Main Contractor Todini | Total for Subcontract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | own | rented |  |
| 1 | Bulldozer | pcs | 8 | 1 | 0 | 0 | 1 |
| 2 | Excavator | pcs | 8 | 2 | 0 | 0 | 2 |
| 3 | Loader | pcs | 9 | 3 | 0 | 0 | 3 |
| 4 | Motor grader | pcs | 4 | 2 | 0 | 0 | 2 |
| 5 | Rollers | pcs | 20 | 3 | 0 | 0 | 3 |
| 6 | Dumpers | pcs | 80 | 5 | 0 | 0 | 5 |
| 7 | Water tank | pcs | 10 | 3 | 0 | 0 | 3 |
| 8 | Petrol tank | pcs | 6 | 1 | 0 | 0 | 1 |
| 9 | Asphalt paver | pcs | 3 | 1 | 0 | 0 | 1 |
| 10 | Concrete paver | pcs | 1 | 1 | 0 | 0 | 1 |
| 11 | Milling machine | pcs | 1 | 0 | 0 | 0 | 0 |
| 12 | Truck crane | pcs | 2 | 3 | 0 | 0 | 3 |
| 13 | Distributor | pcs | 1 | 1 | 0 | 0 | 1 |
| 14 | ACP | pcs | 1 | 1 | 0 | 0 | 1 |
| 15 | CCP | pcs | 1 | 1 | 0 | 0 | 1 |
| 16 | Crusher | pcs | 1 | 1 | 0 | 0 | 1 |
| 17 | Cement warehouse | pcs | 1 | 1 | 0 | 0 | 1 |
| 18 | Sand washer | pcs | 1 | 1 | 0 | 0 | 1 |
| 19 | Trawl (semitrailer) | pcs | - | 0 | 0 | 0 | 0 |
| 20 | Crushing machine | pcs | - | 0 | 0 | 0 | 0 |
| 21 | Batching plant | pcs | 1 | 0 | 0 | 0 | 0 |
| 22 | Other equipment | pcs | - | 0 | 0 | 0 | 0 |
| TOTAL | pcs | 159 | 31 | 0 | 0 | 31 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP “Sine Midas Stroy” | Full complex of works | km214.3- km 259,3 | Approved |

Problem issues:

| 1. | Determination is not available for construction of road to hothouse Agrodos |
| --- | --- |