As per 30.03.2016

INFORMATION

For implementation of section km 259.3 – km 304.4 “Almaty-Khorgos” road

of Western Europe – Western China Project in Almaty Region Lot 6

Main Contractor – JV «Todini /Impregilo-Kazakhdorstroy»

Contract – EWRP-214.3-259.3-ICB(W)-001/2013

Contract amount – 15 670.12 mln. KZT

Contract Amount (new) - 15 946 601 999 KZT

Contract signed – 30.07.2013

Construction period – 22 / 10 / 2013 – 30 / 11 / 2016

Disbursed in 2013-2015 – 10 844 589 288.67 KZT

Disbursement plan for 2016 – 5 102 012 710.33 KZT

Engineer CSC – Sweroad/Gauff/QPEC

Designer – LLP “Kazakhstan zholdary”

- Main Project characteristics

| Length, km | 45 |
| --- | --- |
| Culverts, no’s. | 52 |
| Bridges and cattle creeps, nos. | 0 |
| Overpasses, nos. | 0 |
| Interchanges, no’s. | 2 |
| Earthworks, thous.m3 | 7 238 |
| Sub base, km/thous.m3 | 45 / 458 |
| CSCSM, km/thous.m3 | 45 / 197 |
| Cement concrete pavement, km/thous.m3 | 45 / 219 |

- Analysis for work schedule performance:

| N | Description of works | Total under Contract | Plan for 2016 | Actual for current date since 2016 start | performance vs annual plan | performance vs contract |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Prior to variation | After variation |  |  | остаток/remain | % | остаток/remain | % |
| 1. | Earthworks (thous.m3) | 7 238 | 5 066,8 | 524,7 | 186,1 | 327,1 | 62% | 197,6 | 96% |
|  | Strengthening layer for embankment |  |  |  | 11,5 |  |  |  |  |
| 2. | Subbase, km | 45,0 | 4,32 | 0,05 | 4,27 | 1,2% | 4,27 | 90% |
| 3. | Base course from CSCSM, km | 45,0 | 8,82 | 0,78 | 8,04 | 9% | 8,04 | 82% |
| 4. | Cement concrete pavement, km | 45,0 | 9,39 | 0 | 9,39 | 0% | 9,39 | 79% |
| 5. | Bridges and overpasses, nos. | 0 | 0 | - |  |  |  |  |
| 6. | Culverts, nos. | 58 | - | 58 performed |  | 100% |  | 100% |
|  | Strengthening layer for embankment (culverts) |  |  | 0 |  |  |  |  |

- Procurement of materials for 2016:

| N | Description of material | Total under Contract | Plan for 2016 | Actual for current date since 2016 start | % | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | Crushed stone, thous.m3 | 358,38 | 17,89 | 0 | 0 |  |
| 2. | Sand, thous.m3 | 38,97 | 0,36 | 0 | 0 |  |
| 3. | SGM, thous.m3 | 489,93 | 20,13 | 0 | 0 |  |
| 4. | Cement, thous.m3 | 102,88 | 19,81 | 0,56 | 3,0 |  |
| 5. | RCP, thous.m3 | 3.91 | 0 | 0 | 0 |  |

- Personnel involvement:

| N | Description | Demand for 2016 | TOTAL actual | Main Contractor |
| --- | --- | --- | --- | --- |
|  |  |  |  | TOTAL | foreign | local |
| 1 | Engineers and Technicians, Administration | 34 | 33 | 33 | 13 | 20 |
| 2 | Laboratory Assistants and Quality Service | 8 | 16 | 16 | 1 | 15 |
| 3 | Operators of special machinery | 72 | 29 | 29 | - | 29 |
| 4 | Surveyors | 4 | 15 | 15 | 1 | 14 |
| 5 | Drivers of dumpers | 80 | 60 | 60 | - | 60 |
| 6 | Road workers | 40 | 10 | 10 | - | 10 |
| 7 | Welders |  |  |  |  |  |
| 8 | Drivers of cars | - | 4 | 4 | - | 4 |
|  | TOTAL | 238 | 167 | 167 | 15 | 152 |

- Mobilization of equipment:

| N | Description of equipment | Unit | Demand for 2016 | TOTAL actual | Main Contractor Todini | Total for Subcontractors |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | own | rented |  |
| 1 | Bulldozer | pcs | 8 | 15 | 0 | 0 | 15 |
| 2 | Excavator | pcs | 8 | 16 | 0 | 0 | 16 |
| 3 | Loader | pcs | 9 | 30 | 0 | 0 | 30 |
| 4 | Motor grader | pcs | 4 | 8 | 0 | 0 | 8 |
| 5 | Rollers | pcs | 20 | 15 | 0 | 0 | 15 |
| 6 | Dumpers | pcs | 80 | 60 | 0 | 0 | 60 |
| 7 | Water tank | pcs | 10 | 10 | 0 | 0 | 10 |
| 8 | Petrol tank | pcs | 6 | 0 | 0 | 0 | 0 |
| 9 | Asphalt paver | pcs | 4 | 3 | 0 | 0 | 3 |
| 10 | Concrete paver | pcs | 1 | 1 | 0 | 0 | 1 |
| 11 | Milling machine | pcs | 0 | 0 | 0 | 0 | 0 |
| 12 | Truck crane | pcs | 2 | 6 | 0 | 0 | 6 |
| 13 | Distributor | pcs | 1 | 0 | 0 | 0 | 0 |
| 14 | ACP | pcs | 1 | 0 | 0 | 0 | 0 |
| 15 | CCP | pcs | 1 | 1 | 0 | 0 | 1 |
| 16 | Crusher | pcs | 1 | 1 | 0 | 0 | 1 |
| 17 | Cement warehouse | pcs | 1 | 0 | 0 | 0 | 0 |
| 18 | Sand washer | pcs | 1 | 0 | 0 | 0 | 0 |
| 19 | Trawl (semitrailer) | pcs | 0 | 0 | 0 | 0 | 0 |
| 20 | Crushing machine | pcs | 0 | 0 | 0 | 0 | 0 |
| 21 | Batching plant | pcs | 0 | 0 | 0 | 0 | 0 |
| 22 | Other equipment | pcs | 0 | 9 | 0 | 0 | 9 |
| TOTAL | pcs | 158 | 127 | 0 | 0 | 127 |

- Subcontractors:

| N | Name of Subcontractor | Type of work | Section from km – to km | Remarks |
| --- | --- | --- | --- | --- |
| 1 | LLP “Sine Midas Stroi” | Full complex of works | km259.3- km 304.4 | Approved |

Problem issues:

| 1. | No access to the site of the last kilometer (area of connection). It is not clear for location of Customs Post, coordinates were not determined. In addition, from CH 887+65 to CH 899+64 there is a neutral zone (zone of impact of China), and access is not possible to this section. When determination of location for Customs Post we request you to consider the location of bridges across Khorgos River at CH 873+96 and across Exclusion Zone (EZ) at CH 888+10. |
| --- | --- |

Variations.

| No. | Name | Financial impact | Approval date | Remarks |
| --- | --- | --- | --- | --- |
| 01 | Variation Order Lot 6 | Increase for 529 871 101.21 KZT including VAT | Approved without comments Letter No 23-23-05/416 dated 03.11.2014 |  |
| 02 | Variation Order Lot 6 | Increase for 365 901 682.29 KZT including VAT | Approved with comments Letter No 23-23-05/506 dated 12.11.2014 |  |
| 03 | Variation Order Lot 6 | Reduce for 619 290 836.0 KZT including VAT | Approved with comments Letter No 23-23-05/367 dated 27.10.2014 |  |